## Checklist 1stQ2024
LGU | A.1. Organization |  |  |  | B.2. Training (No. of trainings attended/ Conducted FY 2020) |  |  | C.3. Planning (for 2021) |  |  | D.4. Quarterly Meetings Conducted |  | D.5. Monitoring Visits/ Field Inspection Conducted
| EO or Resolution | Chairman | Date Organized | Updated? | Conducted | Attended | Form 9 submitted | Duly Approved Work & Financial Plan | Duly Approved M & E Plan | Duly Approved M & E Work Program | 4thQ Minutes of Meeting | Resolution (whenever is applicable) | Form 5 | Form 6 | Form 7
SAN JULIAN | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1

## SCORING SYSTEM
Republic of the Philippines
DEPARTMENT OF THE INTERIOR AND LOCAL GOVERNMENT
MUNICIPAL OFFICE
SAN JULIAN E. SAMAR
LPMC FUNCTIONALITY ASSESSMENT TOOL
Quarter Covered:1st QUARTER OF 2024
LGU | INDICATORS |  |  |  |  | TOTAL RATING: | ADJECTIVAL RATING: | Remarks
| ORGANIZATION: (Points) | TRAINING: (Points) | PLANNING: (AWP, M&E Plan & Program 2024) | A. IMPLEMENATION AND REPORTING: (Meeting) | B. IMPLEMENATION AND REPORTING: (Site Visit)
SAN JULIAN | 5 | 0 | 0 | 5 | 5 | 15 | Medium Functionality
ADJECTIVAL RATING
20-25 | High functionality
13-19 | Medium functionality
1-12 | Low fucntionality
0 | No established LPMC
Note: Please refer to Annex A - LPMC Functionality Assessment Technical Guide Notes
Prepared by: | [5 empty] | Approved by:
MARILES G. MONTES
| LPMC Focal | [5 empty] | Provincial Director

## PARAMETERS
Republic of the Philippines
DEPARTMENT OF THE INTERIOR AND LOCAL GOVERNMENT
MUNICIPAL OFFICE
SAN JULIAN EASTERN SAMAR
STATUS REPORT ON THE FUNCTIONALITY OF LOCAL PROJECT MONITORING COMMITEES (LPMCs)
Quarter Covered:1st Q Quarter of 2024
LGU | PARAMETERS | [6 empty] | Remarks
| LPMC Year Organized | EO or Resolution submitted to DILG PO/RO? (Y/N) | List of Members updated and submitted to DILG? (Y/N) | Training on Project Monitoring conducted/ attended at least once a year? (Y/N) | Annual Work Financial Plan submitted to RPMC/DILG? (Y/N) | Accomplishment Report submitted to RPMC/DILG? (Y/N) | Minutes of regular meetings conducted submitted to RPMC/DILG? (Y/N)
SAN JULIAN | 2023 | Y | Y | Y | Y | Y | Y
Note: LPMCs can be considered active and functional if all parameters have been meet.
Approved by:
Prepared by:
MARILES G. MONTES
| LPMC Focal | [5 empty] | Provincial Director

## REFERENCE
REFERENCE

## WorkFinancialPlan
LOCAL PROJECT MONITORING COMMITTEE (LPMC)
WORK AND FINANCIAL PLAN
For CY 2024
PMC: SAN JULIAN
Activity (e.g. quarterly meetings, PSS, trainings, field monitoring activities) | Expected Output | Schedule | Responsible Unit/Individual | Fund Source | Budget (PhP) | Remarks
1. Conduct of Quarterly Meeting | Meeting conducted and documented | Last Monday of the 3rd month of the quarter | LPMC | LGU | P10000
2.Field Monitoring Activities | Field visit conducted | last week of the 3rd month of each quarter | LPMC | LGU | P10000
|  |  | T O T A L |  | 20000
Prepared by: |  | Approved: |  |  | Noted by:
ENGR. FLEURDELIZ C. QUINTO |  | MARILES G. MONTES |  |  | HON. DENNIS P. ESTARON
PMC Secretariat |  | PMC Chairperson |  |  | LCE

## Monitoring and Evaluation Plan
LOCAL PROJECT MONITORING COMMITTEE (LPMC)
MONITORING AND EVALUATION PLAN
For CY 2024
PMC: Balangkayan
Description of Indicators | Baseline Data (Y0) | Target Values (2024) |  |  |  | Sources of Data | Method of Data Collection | Timing/ Frequency | Unit/ Person Responsible to Collect | Unit/ Person Responsible to Report
|  | Qtr 1 (2024) | Qtr 1 (2024) | Qtr 1 (2024) | Qtr 1 (2024)
[6 empty] | Project Status and Fund utilization Report | Data Collection from Mun Engineering Office; Review & validation by LPMC | Quarterly | LPMC Secertariat | LPMC Secertariat
[6 empty] | Project Status and Fund utilization Report | Data Collection from Mun Engineering Office; Review & validation by LPMC | Quarterly | LPMC Secertariat | LPMC Secertariat
[6 empty] | Project Status and Fund utilization Report | Data Collection from Mun Engineering Office; Review & validation by LPMC | Quarterly | LPMC Secertariat | LPMC Secertariat
[6 empty] | Project Status and Fund utilization Report | Data Collection from Mun Engineering Office; Review & validation by LPMC | Quarterly | LPMC Secertariat | LPMC Secertariat
Prepared by: |  | Approved: |  |  | Noted by:
PMC Secretariat |  | PMC Chairperson |  |  | LCE

## MandEWorkProgram
LOCAL PROJECT MONITORING COMMITTEE (LPMC)
PRIORITY PROGRAMS/ PROJECTS TO BE MONITORED
For CY 2024
PMC: SAN JULIAN
Name of Program/ Project | Location | Fund Source | Implementing Agency | Schedule (1st, 2nd, 3rd & 4th Quarter)
1. Site Development of LGU Acquired Lot | Brgy 4 Poblacion San Julian | LGU -20% DF | LGU | March 26,2023
2. Rehabilitation of Campidhan-Putong FMR (Installation of RCBC and Road Reblocking) | Brgy Putong, San Julian E. Samar | LGU -20% DF | LGU | April 30, 2024
3. Construction of Day Care Center | Brgy Libas, San Julian E. Samar | LGU -20% DF | LGU | May 30, 2024
4. Rehabilitation of San Isidro -Canserang FMR | brgy San Isidro, San Julian E. Samar | LGU -20% DF | LGU | June 15, 2024
Prepared by: |  | Approved: |  | Noted by:
ENGR. FLEURDELIZ C. QUINTO |  |  |  | HON. DENNIS P. ESTARON
PMC Secretariat |  | MARILES G. MONTES

## RPMES Form 5
RPMES Form 5
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
SUMMARY OF FINANCIAL AND PHYSICAL ACCOMPLISHMENTS INCLUDING PROJECT RESULTS (BY AREA, SECTOR, AGENCY)
As of First Quarter 2024
PMC: San Julian
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15)
(a) Name of Project & its Components (b)Funding Source (c) Project Schedule | FINANCIAL STATUS (IN PHP M) | [6 empty] | Target to Date | Actual Accomplishment to Date | Slippage | Performance | Employment Generated |  | Remarks
| Output Indicators | Allocation | Releases | Obligations | Disbursements | Funding Support (%) | Fund Utuilization (%)
|  | As of Reporting Period | As of Reporting Period | As of Reporting Period | As of Reporting Period | [6 empty] | (M) | (F)
1. (a) Site Development of LGU Acquired Lot (b) LGU 20% Devt Fund (3)Oct 1, 2023 to Nov 1, 2023 |  | Php910,691.86 | [5 empty] | 100% | 80% | 20%
2. (a) Rehabilitation of Campidhan-Putong FMR (Installation of RCBC and Road Reblocking) ;(b) (b) LGU 20% Devt Fund ; (c ) January 5, 2024- April 3, 2024 |  | Php3240194.76 | [5 empty] | 100% | 61.95% | 38%
3.(a) Construction of Day Care Center (b) LGU 20% Devt Fund ; (c )March 13, 2024- August 9, 2024 |  | Php1990000
4. Rehabilitation of San Isidro -Canserang FMR (b) LGU 20% Devt Fund ; (c )March 18, 2024- May 16, 2024 |  | Php2995000
Submitted by: | MARILES G MONTES | [8 empty] | Noted by: | HON. DENNIS P. ESTARON
Designation/ Office: | PMC Chairperson | [9 empty] | Agency Head
Date: | 2024-01-04
Note: This form was enhanced based on the existing RPMES form and Annual ODA Portfolio Review form Adopted in 2015.

## RPMES Form 6
RPMES Form 6
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
REPORT ON THE STATUS OF PROJECTS ENCOUNTERING IMPLEMENTATION PROBLEMS
As of 1st Quarter 2024
SAN JULIAN
Name of Project/ Program Components | Location | Implementing Agency | Funds Utilization | Physical Status (%) |  |  | Issues | Source of Information | Action Taken/ Recommendations
|  |  |  | Target | Actual | Slippage
1. Site Development of LGU Acquired Lot | Brgy 4 Poblacion San Julian | LGU Mun |  |  |  | 20% | weather ondition | Mun Engineering Office
2. Rehabilitation of Campidhan-Putong FMR (Installation of RCBC and Road Reblocking) | Brgy Putong, San Julian E. Samar | LGU Mun |  |  |  | 38% | weather conditions | Mun Engineering Office
3. Construction of Day Care Center | Brgy Libas, San Julian E. Samar | LGU Mun |  |  |  | 0% | none | Mun Engineering Office
4. Rehabilitation of San Isidro -Canserang FMR | brgy San Isidro, San Julian E. Samar | LGU Mun |  |  |  | 0% | none | Mun Engineering Office
Submitted by: | MARILES G. MONTES
Designation/ Office: | PMC Chairperson
Date: | 2024-01-04

## RPMES Form 7
RPMES Form 7
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
PROJECT INSPECTION REPORT
As of First Quarter 2024
SAN JULIAN
Name of Project/ Program Components | Location | Implementing Agency | Date of Project Inspection | Major Findings | Issues | Action Taken/ Recommendations
Brgy 4 Poblacion San Julian | Brgy 4 Poblacion San Julian | LGU Mun | March 15, 2024 | delayed completion vis-a-vz target | weather condition
Brgy Putong, San Julian E. Samar | Brgy Putong, San Julian E. Samar | LGU Mun
Brgy Libas, San Julian E. Samar | Brgy Libas, San Julian E. Samar | LGU Mun
brgy San Isidro, San Julian E. Samar | brgy San Isidro, San Julian E. Samar | LGU Mun
Submitted by: | MARILES G. MONTES |  |  |  | Noted by: | HON. DENNIS P. ESTARON
Designation/ Office: | PMC Chairman |  |  |  |  | Agency Head
Date:
Note: This is a new form based on the existing RPMES forms Adopted in 2015.

## RPMES Form 9
RPMES Form 9
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
TRAINING / WORKSHOPS
Training/ Workshop Conducted/ Attended in the 1st Quarter 2024
PMC: | SAN JULIAN
Date | Title of Training/ Workshop | Objective of Training/ Workshop | Lead Office/ Unit | Participating Offices/ Agencies/ Organizations | Total No. of Male Participants | Total No. of Female Participants
February 15, 2024 | LPMC Orientation on lpmc Technical Guide Notes | Training Objective: The objective of the "LPMC Orientation on LPMC Technical Guide Notes" is to equip participants with a comprehensive understanding of the LPMC Technical Guide Notes, ensuring they can effectively apply this knowledge in their respective roles. By the end of this training, participants will be able to: 1. Understand the Structure: Navigate through the LPMC Technical Guide Notes, understanding its structure, key sections, and how it’s intended to be used in practical scenarios. 2. Apply Knowledge: Apply the guidelines and best practices outlined in the LPMC Technical Guide Notes to LGU projects, enhancing the quality and efficiency of their work. 3. Identify Resources: Identify and utilize additional resources and tools mentioned in the guide notes to solve complex problems and stay updated with the latest industry standards. 4. Collaborate Effectively: Enhance collaboration among team members by using a common framework and language for technical discussions, as outlined in the guide notes. 5. Continuous Improvement: Foster a mindset of continuous improvement by understanding the mechanism for providing feedback on the guide notes, contributing to its evolution and relevance. Participants are expected to actively engage in interactive sessions, case studies, and practical exercises designed to reinforce the concepts covered in the LPMC Technical Guide Notes. This training is crucial for LPMC members and serves as a valuable refresher f ensuring alignment with the LGU's standards and expectations. | DILG Municipal Office | LGU, CSO LPMC MEMBERS) | 2 | 6
Submitted by: | ENGR. FLEURDELIZ C. QUINTO |  |  | Noted by: | HON. DENNIS P. ESTARON
Designation/ Office: | PPDC/CPDC/ MPDC |  |  | Designation/ Office: | PMC Chairman
Date: | 2024-02-18 |  |  | Date: | 2024-02-18
Note: This is a new form based on the contecnt of RPMES Accomplishment Reports Adopted in 2015.