## RPMES Form 6
RPMES Form 6
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
REPORT ON THE STATUS OF PROJECTS ENCOUNTERING IMPLEMENTATION PROBLEMS
As of 2nd Quarter 2026
LPMC: LGU-Balangkayan
Name of Project/ Program Components | Location | Implementing Agency | Funds Utilization | Physical Status (%) |  |  | Issues | Source of Information | Action Taken/ Recommendations
|  |  |  | Target | Actual | Slippage
1. Const./Concreting of Access Rd. to new Public Cemetery (Completed) | Balangkayan E. Samar | LGU Balangkayan | 100% |  | 100% | 0% | none | Mun Engineering Office
2. Rehab. & Maintenance of Water System (Completed) | Balangkayan E. Samar | LGU Balangkayan | 100% |  | 100% | 0% | none | Mun Engineering Office
3. Rehab./Improvement of Sitio Tabe FMR (Ongoing) | Balangkayan E. Samar | LGU Balangkayan | -on going |  |  |  | none | Mun Engineering Office
Submitted by: | WELSON P. CONTADO |  |  |  |  | Noted by: | HON. ALLAN C. CONTADO, CPA
Designation/ Office: | PMC Chairperson | [5 empty] | Agency Head
Date: | 06/30/2026