## RPMES Form 7
RPMES Form 7
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
PROJECT INSPECTION REPORT
As of First Quarter 2026
LPMC: LGU BALANGKAYAN
Name of Project/ Program Components | Location | Implementing Agency | Date of Project Inspection | Major Findings | Issues | Action Taken/ Recommendations
1. Const./Concreting of Access Rd. to new Public Cemetery (Completed) | Balangkayan E. Samar | LGU Balangkayan | June 29, 2026 | project completed | None
2. Rehab. & Maintenance of Water System (Completed) | Balangkayan E. Samar | LGU Balangkayan | June 29, 2026 | project completed | None
3. Rehab./Improvement of Sitio Tabe FMR (Ongoing) | Balangkayan E. Samar | LGU Balangkayan | for inspection | on-going | none
Submitted by: | WELSON P. CONTADO |  |  |  | Noted by: | HON. ALLAN C. CONTADO, CPA
Designation/ Office: | PMC Chairman |  |  |  |  | Agency Head
Date: | 06/30/2026
Note: This is a new form based on the existing RPMES forms Adopted in 2015.