Republic of the Philippines

Province of Southern Leyte

CITY OF MAASIN

LOCAL PROJECT MONITORING COMMITTEE (LPMC)

WORK AND FINANCIAL PLAN

FY 2026

PMC:  MAASIN CITY

| ACTIVITIES | EXPECTED OUTPUT | SCHEDULE | RESPONSIBLE UNIT 1 INDIVIDUAL | FUND SOURCE | BUDGET | REMARKS |
| --- | --- | --- | --- | --- | --- | --- |
| Conduct Quarterly Meeting | Minutes of Meeting RPMES Form 8 RPMES Form 10 RPMES Form 11 | Every 2nd month in each quarter | LPMC Secretariat LPMC Members | General Fund City Training Fund OCPDC Fund | 50,000.00 |  |
| Formulation and Approval of Annual LPMC Work & Financial Plan & Priority PPAs | Approved Annual Work & Financial Plan & M&E – Priority PPAs | 1st Quarter | LPMC Secretariat | LGU | 20,000.00 |  |
| LPMC Quarterly Inspection | RPMES Form 5 RPMES Form 6 RPMES Form 7 Photo Documentations | Last week of every quarter | LPMC Secretariat | LGU | 12,000.00 |  |
| Submission of Quarterly Reports | Quarterly Report Submitted | Every 1st week of the following month | LPMC Secretariat LPMC Members |  |  |  |
| Training / Orientation on Basic Engineering Concepts and Project Implementation | PMC Members oriented / knowledgeable in basic engineering terms and concepts and on project implementation | 1st Quarter | LPMC Secretariat LPMC Members | General Fund City Training Fund OCPDC Fund | 200,000.00 |  |
| Other Operating Expenses (Office Supplies & Operational Expenses) | Procurement of supplies, catering services, & other expenses | January – December 2026 | LPMC Secretariat | General Fund City Training Fund OCPDC Fund | 100,000.00 |  |
| TOTAL |  |  |  | Php | 382,000.00 |  |

Prepared by:								Approved by:							Noted by:

ENGR. EUFEMIA S. QUIRONG, SO2				HON. DARYL M. COSTILLAS				HON. LUZ V. MERCADO

Engineer II / PMC Secretariat						PMC Chairman						City Mayor