## 2026
LOCAL PROJECT MONITORING COIMMITTEE (LMPC)
MONITORING & EVALUATION (M&E)
20% DF - FY 2026
As of 3rd Quarter
Pre - Bid
4-Square on Process
Bidded
Issued Notice To Proceed
NO. | PAGE No. | AIP CODE |  | OFFICE | NAME OF PROJECT | LOCATION | ESTIMATED AMOUNT | FUND SOURCE | IMPLEMENTING AGENCY | 1st Quarter | 2nd Quarter | 3rd Quarter | 4th Quarter | REMARKS | PRE-BID | PFMAT Form (4-Square) | 1 | 2 | 3
SOCIAL DEVELOPMENT
1 | 137 | 8000-000-2-01-010 | 004-003-033 | OCE | Procurement and Installation of Street Lighting System | Various Barangays | 10000000 | 20%DF - 2026 | LGU- Maasin City | [8 empty] | 1
2 | 132 | 8000-000-2-01-010 | 004-002-001 | OCE | Construction of School Gym Phase II, Libhu Elementary School | Libhu Elementary School | 1000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 | 06/19/26 |  |  | NTP July 15, 2026 |  |  | 1
3 | 135 | 8000-000-2-01-010 | 005-002-008 | OCE | Construction of Home Economics Building Mahayahay Elementary School | Barangay Mahayahay Elementary School | 3000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 | [6 empty] | 1
4 | 138 | 8000-000-2-01-010 | 004-002-010 | OCE | Construction of Mini School Gym, Lib-og Elementary School | Lib-og Elementary School | 4000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 | 06/15/26 |  |  | NTP July 3, 2026 |  |  | 1
5 | 138 | 8000-000-2-01-010 | 004-002-007 | OCE | Construction of School Gym, Guadalupe National High School | Guadalupe National High School | 5000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 | [6 empty] | 1
6 | 147 | 8000-000-2-01-010 | 004-006-003 | OCE | Construction of School Toilet, Maasin City National High School | Maasin City National High School, Barangay Combado | 3000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 | [6 empty] | 1
7 | 133 | 8000-000-2-01-010 | 004-002-011 | OCE | Construction of Mini School Gym, Bato I Elementary School | Bato I Elementary School | 4000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 | [6 empty] | 1
8 | 144 | 8000-000-2-01-010 | 004-002-006 | OCE | Construction of School Gym, Dongon National High School | Dongon National High School | 5000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 | 06/15/26 |  |  | NTP July 3, 2026 |  | 2026-02-05 | 1
9 | 135 | 8000-000-2-01-010 | 004-002-012 | OCE | Construction of Mini School Gym, Tawid Elementary School | Tawid Elementary School | 4000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 | [6 empty] | 1
10 | 145 | 8000-000-2-01-010 | 004-001-037 | OCE | Improvement of Evacuation Center: Barangay Canyuom | Barangay Canyuom | 1000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 | [6 empty] | 1
11 | 135 | 8000-000-2-01-010 | 004-001-038 | OCE | Improvement of Evacuation Center: TOPS | TOPS, Barangay Mantahan | 1000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 | [6 empty] | 1
12 | 134 | 8000-000-2-01-010 | 004-002-013 | OCE | Construction of Mini Gym, Barangay Cabadiangan | Barangay Cabadiangan | 2500000 | 20%DF - 2026 | LGU- Maasin City |  | 04/2026 05/2026 | [6 empty] | 1
13 | 135 | 8000-000-2-01-010 | 004-002-014 | OCE | Construction of Mini Gym, Cabadiangan Elementary School | Barangay Cabadiangan | 2500000 | 20%DF - 2026 | LGU- Maasin City |  | 04/2026 05/2026 | [6 empty] | 1
14 | 132 | 8000-000-2-01-010 | 004-006-002 | OCE | Construction of Comfort Room, Barangay Combado | Barangay Combado | 800000 | 20%DF - 2026 | LGU- Maasin City |  | 04/2026 05/2026 | [6 empty] | 1
15 | 135 | 8000-000-2-01-010 | 008-016-000 | OCE | Rehabilitation and Improvement of Maasin City Nursery Training Center, Barangay Rizal | Nursery, Barangay Rizal | 12000000 | 20%DF - 2026 | LGU- Maasin City |  | 04/2026 05/2026 | [6 empty] | 1
16 | 134 | 8000-000-2-01-010 | 004-004-006 | OCE | Procurement and Installation of Traffic Signal System: R Kangleon corner R. Garces Street, Barangay Tunga-tunga | R Kangleon corner R. Garces Street, Barangay Tunga-tunga | 4500000 | 20%DF - 2026 | LGU- Maasin City |  | 04/2026 05/2026 | [6 empty] | 1
17 | 136 | 8000-000-2-01-010 | 004-001-039 | OCE | Construction of Multi-purpose Building, Barangay Cambooc | Barangay Cambooc | 3000000 | 20%DF - 2026 | LGU- Maasin City |  | 04/2026 05/2026 | [6 empty] | 1
18 | 136 | 8000-000-2-01-010 | 004-001-033 | OCE | Improvement of Multi-purpose Building:. Barangay Cagnituan | Barangay Cagnituan | 2000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 05/2026 | [6 empty] | 1
19 | 136 | 8000-000-2-01-010 | 004-001-017 | OCE | Improvement of Multi-purpose Building: b. Barangay Tomoy-tomoy | Barangay Tomoy-tomoy | 2000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 |  | July 3, 2026 |  |  | 06/19/26 |  | 1
20 | 136 | 8000-000-2-01-010 | 004-001-005 | OCE | Improvement of Multi-purpose Building: Barangay Basak | Barangay Basak | 2000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 | [6 empty] | 1
21 | 135 | 8000-000-2-01-010 | 004-001-025 | OCE | Improvement of Multi-purpose Building: Barangay Mahayahay | Barangay Mahayahay | 3000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 | [6 empty] | 1
22 | 135 | 8000-000-2-01-010 | 004-001-010 | OCE | Improvement of Multi-purpose Building: Barangay Hinapu Gamay | Barangay Hinapu Gamay | 2000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 05/2026 | [6 empty] | 1
23 | 136 | 8000-000-2-01-010 | 004-001-013 | OCE | Improvement of Multi-purpose Building: Barangay Nonok Norte | Barangay Nonok Norte | 2000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 | [6 empty] | 1
24 | 136 | 8000-000-2-01-010 | 004-001-008 | OCE | Improvement of Multi-purpose Building: Barangay Mantahan | Barangay Mantahan | 3000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 | [6 empty] | 1
25 | 136 | 8000-000-2-01-010 | 004-001-029 | OCE | Improvement of Multi-purpose Building: Barangay Pinaskohan | Barangay Pinaskohan | 2000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 | [6 empty] | 1
26 | 136 | 8000-000-2-01-010 | 004-001-035 | OCE | Rehabilitation of Multi-purpose Building and Day Care Center, Barangay Malapoc Norte | Barangay Malapoc Norte | 1000000 | 20%DF - 2026 | LGU- Maasin City |  | 06/01/26 |  |  | NTP June 17, 2026 |  |  |  | 1
27 | 137 | 8000-000-2-01-010 | 005-002-009 | OCE | Construction of Day Care Center, Barangay Lunas | Barangay Lunas | 2000000 | 20%DF - 2026 | LGU- Maasin City |  | 05/2026 06/2026 | [6 empty] | 1
28 | 136 | 8000-000-2-01-010 | 005-002-010 | OCE | Rehabilitation of Day Care Center, Barangay Pasay | Barangay Pasay | 3800000 | 20%DF - 2026 | LGU- Maasin City |  | 04/2026 05/2026 | [6 empty] | 1
29 | 135 | 8000-000-2-01-015 | 004-000-003 | OCV | Construction of Dog Pound | Barangay Rizal | 1000000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | [6 empty] | 1
30 | 137 | 8000-000-2-01-010 | 005-002-011 | OCE | Construction of One Unit One Storey 2-Classroom School Building, Pinaskohan Elementary School | Elementary School, Barangay Pinaskohan | 3000000 | 20%DF - 2026 | LGU- Maasin City |  | 04/2026 05/2026 | [6 empty] | 1
31 |  | 8000-000-2-01-010 | 004-001-040 | OCE | Rehabilitation of Multi-purpose Building, Barangay Acasia | Barangay Acasia | 3000000 | 20%DF - 2026 | LGU- Maasin City |  | 04/2026 05/2026 | July 3, 2026 |  |  | 06/19/26 |  |  | 1
32 |  | 8000-000-2-01-010 | 004-006-006 | OCE | Construction of Comform Room, Bayview Park Area , Barangay Combado | Bayview Park Area, Barangya Combado | 800000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | [6 empty] | 1
33 | 120 | 8000-000-2-01-010 | 005-002-012 | OCE | Rehabilitation of Schools: One-Classroom School Building Gawisan Elementary School | Gawisan Elementary School | 900000 | 20%DF - 2026 | LGU- Maasin City |  | 05/2026 07/2026 | [6 empty] | 1
34 | 111 | 8000-000-2-01-010 | 005-002-013 | OCE | Improvement of One Unit Two Classroom, Hinapu Daku National High School | Hinapu Daku National High School | 2000000 | 20%DF - 2026 | LGU- Maasin City |  | 05/2026 06/2026 | [6 empty] | 1
35 | 111 | 8000-000-2-01-010 | 010-001-000 | OCE | Concreting of School Road access to OVAL Ground, TOPS Elementary School, Barangay Mantahan | TOPS, Barangay Mantahan | 1000000 | 20%DF - 2026 | LGU- Maasin City |  | 05/2026 06/2026 | [6 empty] | 1
36 | 111 | 8000-000-2-01-010 | 008-017-000 | OCE | Construction of Senior Citizen Building, Barangay Manhilo | Baranangay Manhilo | 2000000 | 20%DF - 2026 | LGU- Maasin City | 03/2026 | [6 empty] | 1
37 | 111 | 8000-000-2-01-010 | 010-002-000 | OCE | Construction of TOPS School Gymnasium and Dormitory, Barangay Mantahan | TOPS, Barangay Mantahan | 5000000 | 20%DF - 2026 | LGU- Maasin City |  | 05/2026 06/2026 | [6 empty] | 1
38 | 111 | 8000-000-2-01-010 | 010-003-000 | OCE | Construction of School Gate, Maasin Central School, Barangay. Tunga-tunga | Maasin Central School, Barangay Tunga-tunga | 500000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | [6 empty] | 1
39 | 111 | 8000-000-2-01-010 | 010-004-000 | OCE | Construction of Retaining Wall, Maasin Vocational High School, Barangay Combado | Maasin Vocational High School, Barangay Combado | 2000000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 |  | July 3, 2026 |  |  | 06/19/26 |  | 1
40 | 111 | 8000-000-2-01-010 | 008-018-000 | OCE | Construction of Retaining Wall at Maasin Ajonay Residences Phase I, Barangay Tam-is | Barangay Tam-is | 12454550 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | [6 empty] | 1
41 | 108 | 8000-000-2-01-010 | 010-005-000 | OCE | Construction of School Stage, SPED Center, Barangay Mantahan | SPED Center, Barangay Mantahan | 2000000 | 20%DF - 2026 | LGU- Maasin City |  | 05/2026 06/2026 | [6 empty] | 1
| 110 |  |  |  |  | Sub-total (Social Development) | 126754550
II. ECONOMIC DEVELOPMENT | 109
42 | 112 | 8000-000-2-02-003 | 004-011-011 | OCAg | Procurement of Post-Harvest Facilities: Hand Tractor Cultivator | - | 2000000 | 20%DF - 2026 | LGU- Maasin City | [8 empty] | 1
43 | 105 | 8000-000-2-02-003 | 004-011-006 | OCAg | Procurement of Post-Harvest Facilities: 4-Wheel Tractor | - | 3000000 | 20%DF - 2026 | LGU- Maasin City | [8 empty] | 1
44 |  | 8000-000-2-01-010 | 002-002-046 | OCE | Construction of Local Road: Purok Kolohan, Barangay Lib-og | Purok Kolohan, Barangay Lib-og | 2000000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | 04/27/26 |  |  | NTP May 19, 2026 |  | 2026-02-12 | 1
45 |  | 8000-000-2-01-010 | 002-002-003 | OCE | Construction of Local Road: Sitio Loblobon, Barangay Sto. Nino | Sitio Loblobon, Barangay Sto. Nino | 3000000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | 03/10/26 |  |  | NTP Mar. 26, 2026 | 2026-02-12 |  | 1
46 |  | 8000-000-2-01-010 | 002-002-029 | OCE | Construction of Local Road: Barangay Matin-ao to Barangay Cansirong | Barangay Matin-ao to Barangay Cansirong | 10000000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 |  | July 3, 2026 |  |  | 06/19/26 |  | 1
47 |  | 8000-000-2-01-010 | 002-002-011 | OCE | Construction of Local Road: Barangay Cabadiangan to Barangay Basak | Barangay Cabadiangan to Barangay Basak | 10000000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | 03/10/26 |  |  | NTP Mar. 26, 2026 | 2026-02-12 |  | 1
48 |  | 8000-000-2-01-010 | 002-002-045 | OCE | Construction of Local Road: Sitio Kolo, Barangay Tomoy-tomoy | Sitio Kolo, Barangay Tomoy-tomoy | 1550000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | 02/25/26 |  |  | NTP Mar. 16, 2026 | 2026-02-12 |  | 1
49 |  | 8000-000-2-01-010 | 002-002-021 | OCE | Construction of Local Road:. Sitio Telecom, Barangay Hinapu Daku | Sitio Telecom, Barangay Hinapu Daku | 3200000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | 03/10/26 |  |  | NTP Mar. 26, 2026 | 2026-02-12 |  | 1
50 |  | 8000-000-2-01-010 | 002-002-024 | OCE | Construction of Local Road: Sitio Danao, Barangay Libertad | Sitio Danao, Barangay Libertad | 3000000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | 03/10/26 |  |  | NTP Mar. 26, 2026 | 2026-02-12 |  | 1
51 |  | 8000-000-2-01-010 | 002-002-023 | OCE | Construction of Local Road: Purok Tambis (leading to Isagani Elementary School), Barangay Isagani | Purok Tambis, Barangay Isagani | 500000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | 06/19/26 |  |  | NTP July 15, 2026 |  | 2026-02-05 | 1
52 |  | 8000-000-2-01-010 | 002-002-047 | OCE | Concreting of Local Road, Sitio Kolo, Barangay Cabadiangan | Sitio Kolo, Barangay Cabadiangan | 3000000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | [6 empty] | 1
53 |  | 8000-000-2-01-010 | 002-002-048 | OCE | Concrete Reblocking of Local Road, Barangay Rizal | Barangay Rizal | 2810000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | 03/10/26 |  |  | NTP Mar. 26, 2026 | 2026-02-12 |  | 1
54 |  | 8000-000-2-01-010 | 002-002-042 | OCE | Construction of Local Road Phase III, Purok Nangka, Barangay Lib-og | Purok Nangka, Barangay Lib-og | 2000000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | 04/27/26 |  |  | NTP May 19, 2026 |  |  | 1
55 |  | 8000-000-2-01-010 | 002-002-049 | OCE | Road Widening Phase III at Cabaroy , Barangay Abgao | Cabaroy, Barangay Abgao | 2500000 | 20%DF - 2026 | LGU- Maasin City |  | 05/2026 06/2026 | [6 empty] | 1
56 |  | 8000-000-2-01-010 | 002-002-018 | OCE | Construction of Local Road Phase III, Purok Macopa, Barangay Gawisan | Purok Macopa, Barangay Gawisan | 2000000 | 20%DF - 2026 | LGU- Maasin City | 02/2024 03/2024 |  | July 3, 2026 |  |  | 06/19/26 | 2026-02-05 | 1
57 |  | 8000-000-2-01-010 | 002-003-019 | OCE | Construction of Footbridge,Purok Boguinvilla, Barangay Sta. Cruz | Purok Boguinvilla, Barangay Sta. Cruz | 2000000 | 20%DF - 2026 | LGU- Maasin City |  | 05/2026 06/2026 | [6 empty] | 1
58 |  | 8000-000-2-01-010 | 002-003-020 | OCE | Construction of Footbridge, Sitio Tag-os, Barangay Bilibol | Sitio Tag-os, Barangay Bilibol | 1000000 | 20%DF - 2026 | LGU- Maasin City |  | 05/2026 06/2026 | [6 empty] | 1
59 |  | 8000-000-2-01-010 | 002-003-021 | OCE | Construction of Footbridge, Purok Narra to Purok Banahaw, Barangay Nasaug | Purok Narra to Purok Banahaw, Barangay Nasaug | 2000000 | 20%DF - 2026 | LGU- Maasin City |  | 05/2026 06/2026 | [6 empty] | 1
60 |  | 8000-000-2-01-010 | 002-003-022 | OCE | Construction of Footbridge, Purok Azucena, Barangay Nonok Norte | Purok Azucena, Barangay Nonok Norte | 1000000 | 20%DF - 2026 | LGU- Maasin City |  | 05/2026 06/2026 | [6 empty] | 1
61 |  | 8000-000-2-02-001 | 007-022-000 | CIPTO | Construction of Rest Area in Cagnituan Falls & Guinsohotan Caves Phase II, Barangay Cagnituan | Barangay Cagnituan | 2000000 | 20%DF - 2026 | LGU- Maasin City | 03/2024 | [6 empty] | 1
62 |  | 8000-000-2-01-010 | 002-002-050 | OCE | Construction of Pathway, Purok Imelda Rose, Barangay Bato I | Purok Imelda Rose, Barangay Bato I | 500000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | 06/01/26 |  |  | NTP June 17, 2026 |  |  | 1
63 |  | 8000-000-2-01-010 | 002-002-051 | OCE | Construction of Pathway, Purok Nangka, Barangay Isagani | Purok Nangka, Barangay Isagani | 1000000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | 04/13/26 |  |  | NTP Apr. 27, 2026 |  | 2026-02-05 | 1
64 |  | 8000-000-2-01-010 | 002-002-028 | OCE | Construction of Local Road, Barangay Malapoc Sur to Barangay Bactul II | Barangay Malapoc Sur to Barangay Bactul II | 1500000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | 06/01/26 |  |  | NTP June 17, 2026 |  | 2026-02-05 | 1
65 |  | 8000-000-2-01-010 | 002-011-003 | OCE | Procurement of Water Tanks | Various Barangays | 5000000 | 20%DF - 2026 | LGU- Maasin City | [6 empty] | 2026-01-13 |  | 1
66 |  | 8000-000-2-01-010 | 002-011-002 | OCE | Procurement of Water Pipes | Various Barangays | 5000000 | 20%DF - 2026 | LGU- Maasin City | [6 empty] | 2026-01-13 |  | 1
67 | 105 | 8000-000-2-01-010 | 008-019-000 | OCE | Construction of Commercial Stalls Phase II, Barangay Tunga-tunga | Barangay Tunga-tunga | 1500000 | 20%DF - 2026 | LGU- Maasin City |  | 05/2026 06/2026 | [6 empty] | 1
68 | 112 | 8000-000-2-01-010 | 002-014-000 | OCE | Improvement of Wet Market | Barangay Combado | 2000000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | 04/27/26 |  |  | NTP May 19, 2026 |  |  | 1 | 0
69 | 107 | 8000-000-2-01-010 | 008-012-000 | OCE | Improvement of Tourist Service Center & Rest Area, Barangay Tagnipa | Barangay Tagnipa | 2500000 | 20%DF - 2026 | LGU- Maasin City |  | 05/2026 06/2026 | [6 empty] | 1
70 | 110 | 8000-000-2-01-010 | 008-020-000 | OCE | Rehabilitation of Roofing at Wharf Building, Barangay Abgao | Barangay Abgao | 2500000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | 04/27/26 |  |  | NTP May 19, 2026 |  |  | 1
| 104 |  |  |  |  | Sub-total (Economic Development) | 80060000
III. ENVIRONMENTAL DEVELOPMENT
71 | 112 | 1000-000-2-02-005 | 004-017-000 | OCENRO | Construction of Weigh Bridge at SLF, Barangay Libhu | SLF, Barangay Libhu | 5000000 | 20%DF - 2026 | LGU- Maasin City | 02/2026 03/2026 | 06/15/26 | [5 empty] | 1
72 | 105 | 8000-000-2-01-010 | 003-003-008 | OCE | Construction of Drainage Canal, Maasin Central School, Barangay Tunga-tunga | Maasin Central School, Barangay Tunga-tunga | 2500000 | 20%DF - 2026 | LGU- Maasin City |  | 05/2026 06/2026 | [5 empty] | 0 | 1
73 | 158 | 8000-000-2-01-010 | 003-001-014 | OCE | Rehabilitation of Slope Protection, Barangay Isagani | Barangay Isagani | 1500000 | 20%DF - 2026 | LGU- Maasin City |  | 05/2026 06/2026 | [5 empty] | 0 | 1
| 148 |  |  |  |  | Sub-total (Environmental Development) | 9000000 | [9 empty] | 43 | 30 | 73
176
| 121 |  |  |  |  | TOTAL AMOUNT (20% DF) | 215814550
120
Prepared by:
ENGR. EUFEMIA S. QUIRONG, SO2
Engineer II
Office of the City Planning & Development Coordinator
MONITORING & EVALUATION (M&E)
SEF Funded Projects
Pre - Bid
4-Square on Process
Bidded
Issued Notice To Proceed
NO. | PAGE No. | AIP CODE |  | OFFICE | NAME OF PROJECT | LOCATION | ESTIMATED AMOUNT | FUND SOURCE | IMPLEMENTING AGENCY | 1st Quarter | 2nd Quarter | 3rd Quarter | 4th Quarter | REMARKS | PRE-BID | PFMAT Form (4-Square)
1 |  |  |  | DepED | Repair of Manhilo NHS - 1 Classroom School Building | Manhilo NHS | 700000 | SEF Repair of Manhilo NHS School Building | LGU- Maasin City |  | 06/01/26 |  |  | NTP June 17, 2026 |  | 2026-02-04
2 |  |  |  | DepED | Repair of Bactul I ES - 1 Classroom School Building | Bactul I ES | 698483.34 | SEF Repair of Bactul I ES School Building | LGU- Maasin City |  | 02/25/26 |  |  | NTP Mar. 16, 2026 |  | 2026-01-23
3 |  |  |  | OCE | Rehabilitation of the Main Building in CHU III , Brgy. Manhilo | MCHU III , Manhilo | 300000 | Philhealth Trust Fund - ABTC - rehabilitation of the Main Building in CHU III Located at Brgy. Manhilo | LGU- Maasin City |  | 06/01/26 |  |  | NTP June 17, 2026 | 2026-02-12
4 |  |  |  | DepED | Repair of Manhilo ES - 1 Classroom School Building | Manhilo ES | 700000 | SEF - Repair of Manhilo ES - 1 Classroom School Building | LGU- Maasin City |  | 04/13/26 |  |  | NTP Apr. 27, 2026 |  | 2026-02-04
Prepared by:
ENGR. EUFEMIA S. QUIRONG, SO2
Engineer II
Office of the City Planning & Development Coordinator

## summary
98382271 | 98382271
79000000 | 79000000
13500000 | 13500000
190882271 | 190882271