## Sheet1
RPMES FORM 8
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
PROBLEM SOLVING SESSIONS/FACILITATION MEETING CONDUCTED
As of June 2024
Program/Project Title | Issue Details | Issue Typology | Location | IA | Date of Meeting | Concerned Agencies | Agreements Reached
Construction of Level II Water Supply System at Brgy. Santan, Santa Rita, Samar | Project implementation is delayed with 35.18% slippage, due to insufficient manpower and equipment by the contractor. | Performance of Contractors/Consultants | Brgy. Santan, Santa Rita, Samar | Municipality of Santa Rita, Samar | June 16, 2024 | MEO | Contractor to submit catch up plan NLT June 30, 2024
Submitted by: |  |  |  | Approved by:
Designation/Office: |  |  |  |  | Regional Director
Date: |  |  |  | Date:

## 1st Quarter
RPMES FORM 8
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
PROBLEM SOLVING SESSIONS/FACILITATION MEETING CONDUCTED
As of March 2026
CITY OF MAASIN
Program/Project Title | Issue Details | Issue Typology | Location | IA | Date of Meeting | Concerned Agencies | Agreements Reached
SUPPLY, DELIVERY and INSTALLATION of CLOSED CIRCUIT TELEVISION (CCTV) | Due to the weather condition as a major factor of a project delay | The contructor request for extension 15-20 working days | Variuos Barangay | Maasin City | Febuary 13, 2026 | City Information Technology Unit (CITU) | Contractor to submit catch up plan
Prepared by: | Noted by: |  |  |  | Approved By:
FATIMA T. BERNALES | ENGR. EUFEMIA S. QUIRONG, SO2 |  |  |  | DARYL MERCADO - COSTILLAS
PMC Ass. Secretariat | PMC Head Secretariat |  |  |  | PMC Chairperson
CPDO Staff | ENGINEER II - City Planning and Development Coordinator |  |  |  | Vice President - Liga ng mga Punong Barangay

## 3rd Quarter
RPMES FORM 8
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
PROBLEM SOLVING SESSIONS/FACILITATION MEETING CONDUCTED
As of August 2026
CITY OF MAASIN
Program/Project Title | Issue Details | Issue Typology | Location | IA | Date of Meeting | Concerned Agencies | Agreements Reached
INSTALLATION OF THERMAL HEAT INSULATOR, CEILING & ROOL-UP DOORS OF MAASIN CITY GYM | Due to many activities book in city gym as a major factor of a project delay | The contructor request for extension 20 working days | Tunga-tunga, Maasin City | Maasin City | August 25, 2026 | OCE | Contractor to submit catch up plan
Prepared by: |  | Approved by: |  |  | Noted by:
ENGR. EUFEMIA S. QUIRONG, SO2 |  | HON. DARYL MERCADO - COSTILLAS |  |  | HON. LUZ V. MERCADO
PMC Head Secretariat |  | PMC Chairperson |  |  | City Mayor
ENGINEER II - City Planning and Development Office |  | Vice President - Liga ng mga Punong Barangay

## 2nd Quarter
RPMES FORM 8
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
PROBLEM SOLVING SESSIONS/FACILITATION MEETING CONDUCTED
As of June 2026
CITY OF MAASIN
Program/Project Title | Issue Details | Issue Typology | Location | IA | Date of Meeting | Concerned Agencies | Agreements Reached
INSTALLATION OF THERMAL HEAT INSULATOR, CEILING & ROOL-UP DOORS OF MAASIN CITY GYM | Due to many activities book in city gym as a major factor of a project delay | The contructor request for extension 20 working days | Tunga-tunga, Maasin City | Maasin City | June 25, 2026 | OCE | Contractor to submit catch up plan
Prepared by: | Noted by: |  |  |  | Approved By:
FATIMA T. BERNALES | ENGR. EUFEMIA S. QUIRONG, SO2 |  |  |  | DARYL MERCADO - COSTILLAS
PMC Ass. Secretariat | PMC Head Secretariat |  |  |  | PMC Chairperson
CPDO Staff | ENGINEER II - City Planning and Development Coordinator |  |  |  | Vice President - Liga ng mga Punong Barangay