## Sheet1
RPMES FORM 11
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
KEY LESSONS LEARNED FROM ISSUES RESOLVED AND BEST PRACTICES
In 2024
Program/Project Title | Location | Implementing Agency | Problem/ Issue |  | Strategies/Actions Taken to Resolve the Problem/Issue | Responsible Entity/Key Actors and their Specific Assistance | Lessons learned and Good Practices that could be shared to the NPMC/Other PMCs
|  |  | Nature | Details
Construction of Level II Water Supply System at Brgy. Santan, Santa Rita, Samar | Brgy. Santan, Santa Rita, Samar | Municipality of Santa Rita | Performance of Contractors/Consultants | Project implementation is delayed, due to insufficient manpower and equipment by the contractor. | LPMC facilitated regular meetings and site visits to ensure that the contractor are taking appropriate actions to address the manpower and equipment shortages. | MEO; XYZ Construction | Regular meetings and site visit and encourage the participation of CSOs.
Submitted by: |  |  |  | Approved by:
Designation/Office: |  |  |  |  | Regional Director
Date: |  |  |  | Date:

## 1st Quarter
RPMES FORM 11
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
KEY LESSONS LEARNED FROM ISSUES RESOLVED AND BEST PRACTICES
As of March 2026
PMC: MAASIN CITY
Program/Project Title | Location | Implementing Agency | Problem/ Issue |  | Strategies/Actions Taken to Resolve the Problem/Issue | Responsible Entity/Key Actors and their Specific Assistance | Lessons learned and Good Practices that could be shared to the NPMC/Other PMCs
|  |  | Nature | Details
NONE | NONE | NONE | NONE | NONE | NONE | NONE | NONE
Prepared by: | Submitted by: |  |  |  | Approved by:
FATIMA T. BERNALES | ENGR. EUFEMIA S. QUIRONG, SO2 |  |  |  | DARYL MERCADO - COSTILLAS
PMC Ass. Secretariat | PMC Secretariat |  |  |  | PMC Chairperson
CPDO Staff | ENGINEER II - City Planning and Development Coordinator |  |  |  | Vice President - Liga ng mga Punong Barangay

## 3rd Quarter
RPMES FORM 11
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
KEY LESSONS LEARNED FROM ISSUES RESOLVED AND BEST PRACTICES
As of August 2026
PMC: MAASIN CITY
Program/Project Title | Location | Implementing Agency | Problem/ Issue |  | Strategies/Actions Taken to Resolve the Problem/Issue | Responsible Entity/Key Actors and their Specific Assistance | Lessons learned and Good Practices that could be shared to the NPMC/Other PMCs
|  |  | Nature | Details
NONE | NONE | NONE | NONE | NONE | NONE | NONE | NONE
Prepared & Submitted by: |  |  |  |  | Approved by:
ENGR. EUFEMIA S. QUIRONG, SO2 |  |  |  |  | DARYL MERCADO - COSTILLAS
PMC Secretariat |  |  |  |  | PMC Chairperson
ENGINEER II - City Planning and Development Office |  |  |  |  | Vice President - Liga ng mga Punong Barangay

## 2nd Quarter
RPMES FORM 11
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
KEY LESSONS LEARNED FROM ISSUES RESOLVED AND BEST PRACTICES
As of June 2026
PMC: MAASIN CITY
Program/Project Title | Location | Implementing Agency | Problem/ Issue |  | Strategies/Actions Taken to Resolve the Problem/Issue | Responsible Entity/Key Actors and their Specific Assistance | Lessons learned and Good Practices that could be shared to the NPMC/Other PMCs
|  |  | Nature | Details
NONE | NONE | NONE | NONE | NONE | NONE | NONE | NONE
Prepared by: | Submitted by: |  |  |  | Approved by:
FATIMA T. BERNALES | ENGR. EUFEMIA S. QUIRONG, SO2 |  |  |  | DARYL MERCADO - COSTILLAS
PMC Ass. Secretariat | PMC Secretariat |  |  |  | PMC Chairperson
CPDO Staff | ENGINEER II - City Planning and Development Coordinator |  |  |  | Vice President - Liga ng mga Punong Barangay