## Sheet1
RPMES Form 5
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
SUMMARY OF FINANCIAL AND PHYSICAL ACCOMPLISHMENTS
As of First Quarter 2026
PMC: MAASIN CITY
Program/Project Title | Implementing Agency | Implementation Schedule |  | Sector | Fund Source | Funding Agency | Total Program/Project Cost (PHP) | Financial Status ( in PHP exact figures) | [5 empty] | Physical Accomplishment |  |  | Employment Generated
[8 empty] | Appropriations | Allotment | Obligations | Disbursments | Funding Suppport (%) | Fund Utilization (%) | Target OWPA to date (%) | Actual OWPA to date (%) | Slippage | M | F | Remarks
|  | Start Date (mm-dd-yyyy) | End Date (mm-dd-yyyy)
Procurement and Installation of Street Lighting System | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 10000000
Construction of School Gym Phase II, Libhu Elementary School | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 1000000
Construction of Home Economics Building Mahayahay Elementary School | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 3000000
Construction of Mini School Gym, Lib-og Elementary School | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 4000000
Construction of School Gym, Guadalupe National High School | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 5000000
Construction of School Toilet, Maasin City National High School | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 3000000
Construction of Mini School Gym, Bato I Elementary School | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 4000000
Construction of School Gym, Dongon National High School | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 5000000
Construction of Mini School Gym, Tawid Elementary School | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 4000000
Improvement of Evacuation Center:
a. Barangay Canyuom | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 1000000
b. TOPS | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 1000000
Construction of Mini Gym, Barangay Cabadiangan | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 2500000
Construction of Mini Gym, Cabadiangan Elementary School | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 2500000
Construction of Comfort Room, Barangay Combado | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 800000
Rehabilitation and Improvement of Maasin City Nursery Training Center, Barangay Rizal | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 12000000
Procurement and Installation of Traffic Signal System:
a. R Kangleon corner R. Garces Street, Barangay Tunga-tunga | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 4500000
Construction of Multi-purpose Building, Barangay Cambooc | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 3000000
Improvement of Multi-purpose Building:
a. Barangay Cagnituan | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 2000000
b. Barangay Tomoy-tomoy | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 2000000
c. Barangay Basak | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 2000000
d. Barangay Mahayahay | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 3000000
e. Barangay Hinapu Gamay | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 2000000
f. Barangay Nonok Norte | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 2000000
g. Barangay Mantahan | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 3000000
h. Barangay Pinaskohan | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 2000000
Rehabilitation of Multi-purpose Building and Day Care Center, Barangay Malapoc Norte | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 1000000
Construction of Day Care Center, Barangay Lunas | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 2000000
Rehabilitation of Day Care Center, Barangay Pasay | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 3800000
Construction of Dog Pound | OCV |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 1000000
Construction of One Unit One Storey 2-Classroom School Building, Pinaskohan Elementary School | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 3000000
Rehabilitation of Multi-purpose Building, Barangay Acasia | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 3000000
Construction of Comform Room, Bayview Park Area , Barangay Combado | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 800000
Rehabilitation of Schools:
a. One-Classroom School Building Gawisan Elementary School | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 900000
Improvement of One Unit Two Classroom, Hinapu Daku National High School | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 2000000
Concreting of School Road access to OVAL Ground, TOPS Elementary School, Barangay Mantahan | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 1000000
Construction of Senior Citizen Building, Barangay Manhilo | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 2000000
Construction of TOPS School Gymnasium and Dormitory, Barangay Mantahan | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 5000000
Construction of School Gate, Maasin Central School, Barangay. Tunga-tunga | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 500000
Construction of Retaining Wall, Maasin Vocational High School, Barangay Combado | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 2000000
Construction of Retaining Wall at Maasin Ajonay Residences Phase I, Barangay Tam-is | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 12454550
Construction of School Stage, SPED Center, Barangay Mantahan | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU | 2000000
Procurement of Post-Harvest Facilities:
a. Hand Tractor Cultivator | OCAg |  |  | ECON. DEV. | 20% DF | MAASIN LGU
b. 4-Wheel Tractor | OCAg |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Construction of Local Road:
a. Purok Kolohan, Barangay Lib-og | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
b. Sitio Loblobon, Barangay Sto. Nino | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
c. Barangay Matin-ao to Barangay Cansirong | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
d. Barangay Cabadiangan to Barangay Basak | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
e. Sitio Kolo, Barangay Tomoy-tomoy | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
f. Sitio Telecom, Barangay Hinapu Daku | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
g. Sitio Danao, Barangay Libertad | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
h. Purok Tambis (leading to Isagani Elementary School), Barangay Isagani | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Concreting of Local Road, Sitio Kolo, Barangay Cabadiangan | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Concrete Reblocking of Local Road, Barangay Rizal | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Construction of Local Road Phase III, Purok Nangka, Barangay Lib-og | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Road Widening Phase III at Cabaroy , Barangay Abgao | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Construction of Local Road Phase III, Purok Macopa, Barangay Gawisan | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Construction of Footbridge,Purok Boguinvilla, Barangay Sta. Cruz | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Construction of Footbridge, Sitio Tag-os, Barangay Bilibol | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Construction of Footbridge, Purok Narra to Purok Banahaw, Barangay Nasaug | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Construction of Footbridge, Purok Azucena, Barangay Nonok Norte | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Construction of Rest Area in Cagnituan Falls & Guinsohotan Caves Phase II, Barangay Cagnituan | CIPTO |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Construction of Pathway, Purok Imelda Rose, Barangay Bato I | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Construction of Pathway, Purok Nangka, Barangay Isagani | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Construction of Local Road, Barangay Malapoc Sur to Barangay Bactul II | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Procurement of Water Tanks | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Procurement of Water Pipes | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Construction of Commercial Stalls Phase II, Barangay Tunga-tunga | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Improvement of Wet Market | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Improvement of Tourist Service Center & Rest Area, Barangay Tagnipa | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Rehabilitation of Roofing at Wharf Building, Barangay Abgao | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU
Construction of Weigh Bridge at SLF, Barangay Libhu | OCENRO |  |  | ENVI. DEV. | 20% DF | MAASIN LGU
Construction of Drainage Canal, Maasin Central School, Barangay Tunga-tunga | OCE |  |  | ENVI. DEV. | 20% DF | MAASIN LGU
Rehabilitation of Slope Protection, Barangay Isagani | OCE |  |  | ENVI. DEV. | 20% DF | MAASIN LGU
| Engr. Marietta R. Ancla | [8 empty] | Noted by:
| ICO-City Planning and Development Coordinator | [10 empty] | Daryl M. Costillas
PMC Chairman

## Final
RPMES Form 5
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
SUMMARY OF FINANCIAL AND PHYSICAL ACCOMPLISHMENTS
As of First Quarter 2026
PMC: MAASIN CITY
Program/Project Title | Implementing Agency | Implementation Schedule |  | Sector | Fund Source | Funding Agency | Total Program/Project Cost (PHP) | Financial Status ( in PHP exact figures) | [5 empty] | Physical Accomplishment |  |  | Employment Generated
[8 empty] | Appropriations | Allotment | Obligations | Disbursments | Funding Suppport (%) | Fund Utilization (%) | Target OWPA to date (%) | Actual OWPA to date (%) | Slippage | M | F | Remarks
|  | Start Date (mm-dd-yyyy) | End Date (mm-dd-yyyy)
Installation of Closed Circuit Television (CCTV) |  | February 7,2026 | March 10,2026 | SOCIAL DEV. | SGLGIF | MAASIN LGU | 1997602 | 2000000 |  |  |  | 100% | 0% | 100% | 60% | -40 | 16 |  | ONGOING
Procurement and Installation of Street Lighting System | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU |  | 10000000
Construction of School Gym, Guadalupe National High School | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU |  | 5000000
Construction of School Gym, Dongon National High School | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU |  | 5000000
Improvement of Evacuation Center:
Rehabilitation and Improvement of Maasin City Nursery Training Center, Barangay Rizal | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU |  | 12000000 | [10 empty] | Formulated POW
Rehabilitation of Schools:
Construction of Retaining Wall at Maasin Ajonay Residences Phase I, Barangay Tam-is | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU |  | 12454550
Construction of Local Road:
c. Barangay Matin-ao to Barangay Cansirong | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU |  | 10000000 | [10 empty] | Not yet BID
d. Barangay Cabadiangan to Barangay Basak | OCE | March 26,2026 |  | ECON. DEV. | 20% DF | MAASIN LGU |  | 10000000
Procurement of Water Tanks | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU |  | 5000000
Procurement of Water Pipes | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU |  | 5000000
Construction of Weigh Bridge at SLF, Barangay Libhu | OCENRO |  |  | ENVI. DEV. | 20% DF | MAASIN LGU |  | 5000000
Prepared by: | [5 empty] | Reviewed by: | [6 empty] | Approved by:
FATIMA T. BERNALES | [5 empty] | ENGR. EUFEMIA S. QUIRONG, SO2 | [6 empty] | DARYL MERCADO - COSTILLAS
PMC Ass. Secretariat | [5 empty] | PMC Head Secretariat | [6 empty] | PMC Chairperson
CPDO Staff | [5 empty] | ENGINEER II - City Planning and Development Coordinator | [6 empty] | Vice President - Liga ng mga Punong Barangay

## 3rd Quarter
RPMES Form 5
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
SUMMARY OF FINANCIAL AND PHYSICAL ACCOMPLISHMENTS
As of 3rd Quarter 2026
PMC: MAASIN CITY
Program/Project Title | Implementing Agency | Implementation Schedule |  | Sector | Fund Source | Funding Agency | Total Program/Project Cost (PHP) | Financial Status ( in PHP exact figures) | [5 empty] | Physical Accomplishment |  |  | Employment Generated
[8 empty] | Appropriations | Allotment | Obligations | Disbursments | Funding Suppport (%) | Fund Utilization (%) | Target OWPA to date (%) | Actual OWPA to date (%) | Slippage | M | F | Remarks
|  | Start Date (mm-dd-yyyy) | End Date (mm-dd-yyyy)
Installation of Closed Circuit Television (CCTV) |  | February 7,2026 | March 10,2026 | SOCIAL DEV. | SGLGIF | MAASIN LGU | 1997602 | 2000000 |  |  |  | 100% | 100% | 100% | 100% |  | 16 |  | COMPLETED
Procurement and Installation of Street Lighting System | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU |  | 10000000
Construction of School Gym, Guadalupe National High School | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU |  | 5000000
Construction of School Gym, Dongon National High School | OCE | July 3,2026 |  | SOCIAL DEV. | 20% DF | MAASIN LGU |  | 5000000 |  |  |  | 100% | 0% | [5 empty] | ONGOING
Improvement of Evacuation Center:
Rehabilitation and Improvement of Maasin City Nursery Training Center, Barangay Rizal | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU |  | 12000000 | [10 empty] | Formulated POW
Rehabilitation of Schools:
Construction of Retaining Wall at Maasin Ajonay Residences Phase I, Barangay Tam-is | OCE |  |  | SOCIAL DEV. | 20% DF | MAASIN LGU |  | 12454550
Construction of Local Road:
Barangay Matin-ao to Barangay Cansirong | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU |  | 10000000 | [10 empty] | BID OPENING 07/03/26
Barangay Cabadiangan to Barangay Basak | OCE | April 01,2026 | September 27,2026 | ECON. DEV. | 20% DF | MAASIN LGU | 9985927.13 | 10000000 |  |  |  | 100% |  |  | 0.58% |  | 15 |  | ONGOING
Procurement of Water Tanks | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU | 5000000 | 5000000 |  |  |  | 100% | [6 empty] | BID
Procurement of Water Pipes | OCE |  |  | ECON. DEV. | 20% DF | MAASIN LGU | 5000000 | 5000000 |  |  |  | 100% | [6 empty] | BID
Construction of Weigh Bridge at SLF, Barangay Libhu | OCENRO |  |  | ENVI.DEV. | 20% DF | MAASIN LGU |  | 5000000
Prepared by: | [5 empty] | Approved by: | [7 empty] | Noted by:
ENGR. EUFEMIA S. QUIRONG, SO2 | [5 empty] | HON. DARYL MERCADO - COSTILLAS | [7 empty] | HON. LUZ V. MERCADO
PMC Head Secretariat | [5 empty] | PMC Chairman | [7 empty] | City Mayor
ENGINEER II - City Planning and Development Office | [5 empty] | Vice President - Liga ng mga Punong Barangay