## Sheet1
RPMES FORM 6
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
REPORT ON THE STATUS OF PROJECTS ENCOUNTERING IMPLEMENTATION PROBLEMS
As of June 2024
Program/Project Title | Location | IA | Fund Utilization (%) | Physical Accomplishment |  |  | Issue Details | Issue Typology | Issue Status | Source of Information | Actions Taken | Actions to be Taken | For NPMC Action (Y/N) | Requested Actions from the NPMC
|  |  |  | Target OWPA to date (%) | Actual OWPA to date (%) | Slippage
Construction of Level II Water Supply System at Brgy. Santan, Santa Rita, Samar | Brgy. Santan, Santa Rita, Samar | Municipality of Santa Rita, Samar | 64.8199 | 100 | 64.82 | -35.18 | • High negative slippage signifying delay in project implementation • Deployed manpower on site less than target as a major factor of project delay. (Target: 20; Actual Deployed: 10) | Performance of Contractors/Consultants | Current | Municipal Engineering Office (MEO); XYZ Construction | The LPMC facilitated a meeting with the MEO and contractor to thresh out the issues. The LPMC demanded the contractor to submit a catch up plan. | Contractor to submit a catch up plan | N | None
0
0
0
0
0
0
0
0
Submitted by: | [5 empty] | Approved by:
Designation/Office: | [6 empty] | Regional Director
Date: | [5 empty] | Date:

## 1st Quarter
RPMES FORM 6
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
REPORT ON THE STATUS OF PROJECTS ENCOUNTERING IMPLEMENTATION PROBLEMS
As of June 2026
MAASIN CITY
Program/Project Title | Location | IA | Fund Utilization (%) | Physical Accomplishment |  |  | Issue Details | Issue Typology | Issue Status | Source of Information | Actions Taken | Actions to be Taken | For NPMC Action (Y/N) | Requested Actions from the NPMC
|  |  |  | Target OWPA to date (%) | Actual OWPA to date (%) | Slippage
SUPPLY, DELIVERY and INSTALLATION of CLOSED CIRCUIT TELEVISION (CCTV) | BRGY. MAMBAJAO, ABGAO, TUNGA-TUNGA, TAGNIPA, COMBADO, MAASIN CITY | CITY OF MAASIN | 0% | 100 | 60 | -40 | • High negative slippage signifying delay in project implementation • Due to the weather condition as a major factor of project delay. | Performance of Contractors/Consultants | Current | Municipal Engineering Office (MEO); XYZ Construction | The LPMC facilitated a meeting with the MEO and contractor to thresh out the issues. The LPMC demanded the contractor to submit a catch up plan. | Contractor to submit a catch up plan | N | None
0
0
0
0
0
0
0
0
Prepared by: |  |  |  | Reviewed by: | [6 empty] | Approved By:
FATIMA T. BERNALES |  |  |  | ENGR. EUFEMIA S. QUIRONG, SO2 | [6 empty] | DARYL MERCADO - COSTILLAS
PMC Ass. Secretariat |  |  |  | PMC Secretariat | [6 empty] | PMC Chairperson
CPDO Staff |  |  |  | ENGINEER II - City Planning and Development Coordinator | [6 empty] | Vice President - Liga ng mga Punong Barangay

## 3rd Quarter
RPMES FORM 6
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
REPORT ON THE STATUS OF PROJECTS ENCOUNTERING IMPLEMENTATION PROBLEMS
As of August 2026
MAASIN CITY
Program/Project Title | Location | IA | Fund Utilization (%) | Physical Accomplishment |  |  | Issue Details | Issue Typology | Issue Status | Source of Information | Actions Taken | Actions to be Taken | For NPMC Action (Y/N) | Requested Actions from the NPMC
|  |  |  | Target OWPA to date (%) | Actual OWPA to date (%) | Slippage
SUPPLY, DELIVERY and INSTALLATION of CLOSED CIRCUIT TELEVISION (CCTV) | BRGY. MAMBAJAO, ABGAO, TUNGA-TUNGA, TAGNIPA, COMBADO, MAASIN CITY | CITY OF MAASIN | 100% | 100 | 100 | 0 | • High negative slippage signifying delay in project implementation • Due to the weather condition as a major factor of project delay. | Performance of Contractors/Consultants | Current | Municipal Engineering Office (MEO); XYZ Construction | The LPMC facilitated a meeting with the MEO and contractor to thresh out the issues. The LPMC demanded the contractor to submit a catch up plan. | Contractor to submit a catch up plan | N | None
Installation of Thermal Heat Insulator, Ceiling & Rool-up Doors of Maasin City Gym | Maasin City GYM, Tunga-tunga Maasin City | CITY OF MAASIN | 100% | 100 | 100 | 0 | Due to many activies held at city gym project will delay | Performance of Contractors/Consultants | Current | Municipal Engineering Office (MEO); XYZ Construction | The LPMC facilitated a meeting with the MEO and contractor to thresh out the issues. The LPMC demanded the contractor to submit a catch up plan.
0
0
Prepared by: | [5 empty] | Approved by: | [5 empty] | Noted by:
ENGR. EUFEMIA S. QUIRONG, SO2 | [5 empty] | HON. DARYL MERCADO - COSTILLAS | [5 empty] | HON. LUZ V. MERCADO
PMC Secretariat | [5 empty] | PMC Chairperson | [5 empty] | City Mayor
ENGINEER II - City Planning and Development Office | [5 empty] | Vice President - Liga ng mga Punong Barangay

## 2nd Quarter
RPMES FORM 6
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
REPORT ON THE STATUS OF PROJECTS ENCOUNTERING IMPLEMENTATION PROBLEMS
As of June 2026
MAASIN CITY
Program/Project Title | Location | IA | Fund Utilization (%) | Physical Accomplishment |  |  | Issue Details | Issue Typology | Issue Status | Source of Information | Actions Taken | Actions to be Taken | For NPMC Action (Y/N) | Requested Actions from the NPMC
|  |  |  | Target OWPA to date (%) | Actual OWPA to date (%) | Slippage
SUPPLY, DELIVERY and INSTALLATION of CLOSED CIRCUIT TELEVISION (CCTV) | BRGY. MAMBAJAO, ABGAO, TUNGA-TUNGA, TAGNIPA, COMBADO, MAASIN CITY | CITY OF MAASIN | 100% | 100 | 100 | 0 | • High negative slippage signifying delay in project implementation • Due to the weather condition as a major factor of project delay. | Performance of Contractors/Consultants | Current | Municipal Engineering Office (MEO); XYZ Construction | The LPMC facilitated a meeting with the MEO and contractor to thresh out the issues. The LPMC demanded the contractor to submit a catch up plan. | Contractor to submit a catch up plan | N | None
Installation of Thermal Heat Insulator, Ceiling & Rool-up Doors of Maasin City Gym | Maasin City GYM, Tunga-tunga Maasin City | CITY OF MAASIN | 40% |  |  | 0 | Due to many activies held at city gym project will delay | Performance of Contractors/Consultants | Current | Municipal Engineering Office (MEO); XYZ Construction | The LPMC facilitated a meeting with the MEO and contractor to thresh out the issues. The LPMC demanded the contractor to submit a catch up plan.
0
0
0
0
0
0
0
Prepared by: |  |  |  | Reviewed by: | [6 empty] | Approved By:
FATIMA T. BERNALES |  |  |  | ENGR. EUFEMIA S. QUIRONG, SO2 | [6 empty] | DARYL MERCADO - COSTILLAS
PMC Ass. Secretariat |  |  |  | PMC Secretariat | [6 empty] | PMC Chairperson
CPDO Staff |  |  |  | ENGINEER II - City Planning and Development Coordinator | [6 empty] | Vice President - Liga ng mga Punong Barangay