## Sheet1
RPMES FORM 7
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
PROJECT INSPECTION REPORT
As of June 2024
Program/Project Title | Total Program/Project Cost (PHP) | Location | IA | Date of Project Inspection | Details on Site(s) Inspected | Findings |  | Issues | Actions Taken | Actions to be Taken
Construction of Level II Water Supply System at Brgy. Santan, Santa Rita, Samar | 2196829.79 | Brgy. Santan, Santa Rita, Samar | Municipality of Santa Rita, Samar | June 16, 2024 | ▸ Date Started: 04/01/2024 ▸ Completion Date: 06/30/2024 ▸ Cost: ₱2,196,829.79 ▸ Physical Status: Ongoing at 65.82% ▸ Financial Status: 65.82% | Poorly designed and installed water pipelines: *Unprotected or visible pipelines; *Hanging with no support structure *PCB to GI Pipe. No proper conversion joint *No water meter |  | Prone to damage and contamination | Inform the Engineering Office, LCE, and report to the LDC | Follow-up the Engineering Office for appropriate action
Submitted by: | [5 empty] | Approved by:
Designation/Office: | [6 empty] | Regional Director
Date: | [5 empty] | Date:
Note on B7: ====== ID#AAABNsJEwZE DILG-0442 (2024-05-16 08:23:06) ▸ The official title as indicated in official project documents (e.g., loan/grant agreement for ODA, contracts, budget ¦ National Economic and Development Authority documents).
Note on D7: ====== ID#AAABNsJEwYQ DILG-0442 (2024-05-16 08:23:06) ▸ Total project cost of the project, in exact PHP figures.
Note on E7: ====== ID#AAABNroeHzw DILG-0442 (2024-05-16 08:23:06) ▸ Barangay/municipality/city/province where the project is implemented.
Note on F7: ====== ID#AAABNroeH0A DILG-0442 (2024-05-16 08:23:06) ▸ Name of Agency/GOCC/LGU/PPMCs/HUCs/SUCs RLAs that implements the program/project.
Note on G7: ====== ID#AAABNsJEwZA DILG-0442 (2024-05-16 08:23:06) ▸ Month, day, year when the project inspection was conducted.
Note on H7: ====== ID#AAABNroeHzA DILG-0442 (2024-05-16 08:23:06) ▸ Indicate the location of the site/s inspected and exact project component/outputs/facilities covered and the corresponding details on: ▸ Date Started ▸ Completion Date ▸ Cost ▸ Physical Status ▸ Financial Status
Note on I7: ====== ID#AAABNroeHzk DILG-0442 (2024-05-16 08:23:06) ▸ Indicate major observations during the project inspection, including latest physical status of the project (i.e., Ahead, On, or Behind Schedule), assessment on the completeness, condition, quality and compliance to design/standards of the components/outputs/facilities. ▸ Findings may include observations on emerging outcomes, damaged outputs, lessons learned, and best practices which may be replicated by other implementing agencies.
Note on K7: ====== ID#AAABNsJEwZM DILG-0442 (2024-05-16 08:23:06) ▸ Operational concerns/constraints identified/ observed/discussed during the site inspections causing the negative findings, which may have policy implications or needing action from concerned agencies and other stakeholders.
Note on L7: ====== ID#AAABNsJEwYs DILG-0442 (2024-05-16 08:23:06) ▸ Remedial measures taken by the concerned agencies and stakeholder to address issues and improve work progress.
Note on M7: ====== ID#AAABNsJEwZo DILG-0442 (2024-05-16 08:23:06) ▸ Indicate specific actions to be carried out by the RPMCs, concerned agencies and stakeholders, and timeline.

## 1st Quarter
RPMES FORM 7
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
PROJECT INSPECTION REPORT
As of March 2026
PMC: MAASIN CITY
Program/Project Title | Total Program/Project Cost (PHP) | Location | IA | Date of Project Inspection | Details on Site(s) Inspected | Findings |  | Issues | Actions Taken | Actions to be Taken
Installation of Closed Circuit Television (CCTV) | 2000000 | Various Barangays | Maasin City | 02/13/2026 | ▸ Date Started: 02/07/2026 ▸ Completion Date: 03/10/2026 ▸ Cost: ₱2,000,000.00 ▸ Physical Status: Ongoing at 60% ▸Financial Status: 100% | the project delay |  | Due to the weather condition the project will delayed | The LPMC demanded the contractor to submit a weather report. | Contractor to submit a weather report
Installition of Thermal Heat, Insulator, Ceiling & Roll-up Doors
Prepared by: |  | Submitted by: |  |  |  |  | Approved by:
FATIMA T. BERNALES |  | ENGR. EUFEMIA S. QUIRONG, SO2 |  |  |  |  | DARYL MERCADO - COSTILLAS
PMC Ass. Secretariat |  | PMC Secretariat |  |  |  |  | PMC Chairperson
CPDO Staff |  | ENGINEER II - City Planning and Development Coordinator |  |  |  |  | Vice President - Liga ng mga Punong Barangay
Note on B7: ====== ID#AAABNsJEwZE DILG-0442 (2024-05-16 08:23:06) ▸ The official title as indicated in official project documents (e.g., loan/grant agreement for ODA, contracts, budget ¦ National Economic and Development Authority documents).
Note on D7: ====== ID#AAABNsJEwYQ DILG-0442 (2024-05-16 08:23:06) ▸ Total project cost of the project, in exact PHP figures.
Note on E7: ====== ID#AAABNroeHzw DILG-0442 (2024-05-16 08:23:06) ▸ Barangay/municipality/city/province where the project is implemented.
Note on F7: ====== ID#AAABNroeH0A DILG-0442 (2024-05-16 08:23:06) ▸ Name of Agency/GOCC/LGU/PPMCs/HUCs/SUCs RLAs that implements the program/project.
Note on G7: ====== ID#AAABNsJEwZA DILG-0442 (2024-05-16 08:23:06) ▸ Month, day, year when the project inspection was conducted.
Note on H7: ====== ID#AAABNroeHzA DILG-0442 (2024-05-16 08:23:06) ▸ Indicate the location of the site/s inspected and exact project component/outputs/facilities covered and the corresponding details on: ▸ Date Started ▸ Completion Date ▸ Cost ▸ Physical Status ▸ Financial Status
Note on I7: ====== ID#AAABNroeHzk DILG-0442 (2024-05-16 08:23:06) ▸ Indicate major observations during the project inspection, including latest physical status of the project (i.e., Ahead, On, or Behind Schedule), assessment on the completeness, condition, quality and compliance to design/standards of the components/outputs/facilities. ▸ Findings may include observations on emerging outcomes, damaged outputs, lessons learned, and best practices which may be replicated by other implementing agencies.
Note on K7: ====== ID#AAABNsJEwZM DILG-0442 (2024-05-16 08:23:06) ▸ Operational concerns/constraints identified/ observed/discussed during the site inspections causing the negative findings, which may have policy implications or needing action from concerned agencies and other stakeholders.
Note on L7: ====== ID#AAABNsJEwYs DILG-0442 (2024-05-16 08:23:06) ▸ Remedial measures taken by the concerned agencies and stakeholder to address issues and improve work progress.
Note on M7: ====== ID#AAABNsJEwZo DILG-0442 (2024-05-16 08:23:06) ▸ Indicate specific actions to be carried out by the RPMCs, concerned agencies and stakeholders, and timeline.

## 3rd Quarter
RPMES FORM 7
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
PROJECT INSPECTION REPORT
As of August 2026
PMC: MAASIN CITY
Program/Project Title | Total Program/Project Cost (PHP) | Location | IA | Date of Project Inspection | Details on Site(s) Inspected | Findings | Issues | Actions Taken | Actions to be Taken
Improvement Of Wet Market | 2000000 | Barangay Combado | Maasin City | 08/25/2026 | ▸ Date Started: 05/20/2026 ▸ Completion Date: 09/02/2026 ▸ Cost: ₱2,000,000.00 ▸ Physical Status: Completed at 100% ▸Financial Status: 100% | Project completed | One of the item which is the rubberised floor painting, was easily peeled off. | The LPMC ask the implementing office to tell the contractor to do repair on the issue. | The contractor repair the issue.
Rehabilitation Of Roofing at Wharf Building | 2500000 | Barangay Abgao | Maasin City | 08/25/2026 | ▸ Date Started: 05/20/2026 ▸ Completion Date: 09/17/2026 ▸ Cost: ₱2,491,334.75 ▸ Physical Status: Ongoing at 61.51% ▸Financial Status: 60% | Project ongoing | So far the site issue was the cleanliness of the area. | The LPMC ask the implementing office to tell the contractor to clean the site area. | The contractor promise to clean the area.
Prepared & Submitted by: |  |  | Approved by: |  |  |  | Noted by:
ENGR. EUFEMIA S. QUIRONG, SO2 |  |  | HON. DARYL MERCADO - COSTILLAS |  |  |  | HON. LUZ V. MERCADO
PMC Secretariat |  |  | PMC Chairperson |  |  |  | City Mayor
ENGINEER II - City Planning and Development Office |  |  | Vice President - Liga ng mga Punong Barangay
Note on B7: ====== ID#AAABNsJEwZE DILG-0442 (2024-05-16 08:23:06) ▸ The official title as indicated in official project documents (e.g., loan/grant agreement for ODA, contracts, budget ¦ National Economic and Development Authority documents).
Note on D7: ====== ID#AAABNsJEwYQ DILG-0442 (2024-05-16 08:23:06) ▸ Total project cost of the project, in exact PHP figures.
Note on E7: ====== ID#AAABNroeHzw DILG-0442 (2024-05-16 08:23:06) ▸ Barangay/municipality/city/province where the project is implemented.
Note on F7: ====== ID#AAABNroeH0A DILG-0442 (2024-05-16 08:23:06) ▸ Name of Agency/GOCC/LGU/PPMCs/HUCs/SUCs RLAs that implements the program/project.
Note on G7: ====== ID#AAABNsJEwZA DILG-0442 (2024-05-16 08:23:06) ▸ Month, day, year when the project inspection was conducted.
Note on H7: ====== ID#AAABNroeHzA DILG-0442 (2024-05-16 08:23:06) ▸ Indicate the location of the site/s inspected and exact project component/outputs/facilities covered and the corresponding details on: ▸ Date Started ▸ Completion Date ▸ Cost ▸ Physical Status ▸ Financial Status
Note on I7: ====== ID#AAABNroeHzk DILG-0442 (2024-05-16 08:23:06) ▸ Indicate major observations during the project inspection, including latest physical status of the project (i.e., Ahead, On, or Behind Schedule), assessment on the completeness, condition, quality and compliance to design/standards of the components/outputs/facilities. ▸ Findings may include observations on emerging outcomes, damaged outputs, lessons learned, and best practices which may be replicated by other implementing agencies.
Note on K7: ====== ID#AAABNsJEwZM DILG-0442 (2024-05-16 08:23:06) ▸ Operational concerns/constraints identified/ observed/discussed during the site inspections causing the negative findings, which may have policy implications or needing action from concerned agencies and other stakeholders.
Note on L7: ====== ID#AAABNsJEwYs DILG-0442 (2024-05-16 08:23:06) ▸ Remedial measures taken by the concerned agencies and stakeholder to address issues and improve work progress.
Note on M7: ====== ID#AAABNsJEwZo DILG-0442 (2024-05-16 08:23:06) ▸ Indicate specific actions to be carried out by the RPMCs, concerned agencies and stakeholders, and timeline.

## 2nd Quarter
RPMES FORM 7
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
PROJECT INSPECTION REPORT
As of June 2026
PMC: MAASIN CITY
Program/Project Title | Total Program/Project Cost (PHP) | Location | IA | Date of Project Inspection | Details on Site(s) Inspected | Findings |  | Issues | Actions Taken | Actions to be Taken
Installation of Closed Circuit Television (CCTV) | 2000000 | Various Barangays | Maasin City | 06/25/2026 | ▸ Date Started: 02/07/2026 ▸ Completion Date: 03/10/2026 ▸ Cost: ₱2,000,000.00 ▸ Physical Status: Ongoing at 60% ▸Financial Status: 100% | the project delay |  | Due to the weather condition the project will delayed | The LPMC demanded the contractor to submit a weather report. | Contractor to submit a weather report
Installition of Thermal Heat, Insulator, Ceiling & Roll-up Doors | 11991868.72 | Maasin City Gym, Tunga-Tunga Maasin City | Maasin City | 06/25/2026 | ▸ Date Started: 02/03/2026 ▸ Completion Date: 09/26/2026 ▸ Cost: ₱4,793,999.91.00 ▸ Physical Status: Ongoing at % ▸Financial Status: 40% | the project delay |  | Due to many activities to be held in city gym, the project will stop. | The LPMC demanded the contractor to submit a cath -up plan. | Contractor to submit a catch up plan
Prepared by: |  | Submitted by: |  |  |  |  | Approved by:
FATIMA T. BERNALES |  | ENGR. EUFEMIA S. QUIRONG, SO2 |  |  |  |  | DARYL MERCADO - COSTILLAS
PMC Ass. Secretariat |  | PMC Secretariat |  |  |  |  | PMC Chairperson
CPDO Staff |  | ENGINEER II - City Planning and Development Coordinator |  |  |  |  | Vice President - Liga ng mga Punong Barangay
Note on B7: ====== ID#AAABNsJEwZE DILG-0442 (2024-05-16 08:23:06) ▸ The official title as indicated in official project documents (e.g., loan/grant agreement for ODA, contracts, budget ¦ National Economic and Development Authority documents).
Note on D7: ====== ID#AAABNsJEwYQ DILG-0442 (2024-05-16 08:23:06) ▸ Total project cost of the project, in exact PHP figures.
Note on E7: ====== ID#AAABNroeHzw DILG-0442 (2024-05-16 08:23:06) ▸ Barangay/municipality/city/province where the project is implemented.
Note on F7: ====== ID#AAABNroeH0A DILG-0442 (2024-05-16 08:23:06) ▸ Name of Agency/GOCC/LGU/PPMCs/HUCs/SUCs RLAs that implements the program/project.
Note on G7: ====== ID#AAABNsJEwZA DILG-0442 (2024-05-16 08:23:06) ▸ Month, day, year when the project inspection was conducted.
Note on H7: ====== ID#AAABNroeHzA DILG-0442 (2024-05-16 08:23:06) ▸ Indicate the location of the site/s inspected and exact project component/outputs/facilities covered and the corresponding details on: ▸ Date Started ▸ Completion Date ▸ Cost ▸ Physical Status ▸ Financial Status
Note on I7: ====== ID#AAABNroeHzk DILG-0442 (2024-05-16 08:23:06) ▸ Indicate major observations during the project inspection, including latest physical status of the project (i.e., Ahead, On, or Behind Schedule), assessment on the completeness, condition, quality and compliance to design/standards of the components/outputs/facilities. ▸ Findings may include observations on emerging outcomes, damaged outputs, lessons learned, and best practices which may be replicated by other implementing agencies.
Note on K7: ====== ID#AAABNsJEwZM DILG-0442 (2024-05-16 08:23:06) ▸ Operational concerns/constraints identified/ observed/discussed during the site inspections causing the negative findings, which may have policy implications or needing action from concerned agencies and other stakeholders.
Note on L7: ====== ID#AAABNsJEwYs DILG-0442 (2024-05-16 08:23:06) ▸ Remedial measures taken by the concerned agencies and stakeholder to address issues and improve work progress.
Note on M7: ====== ID#AAABNsJEwZo DILG-0442 (2024-05-16 08:23:06) ▸ Indicate specific actions to be carried out by the RPMCs, concerned agencies and stakeholders, and timeline.