Republic of the Philippines

PROVINCE OF SOUTHERN LEYTE

Municipality of Hinunangan

LOCAL PROJECT MONITORING COMMITTEE

==========================================================================================

2nd QUARTER MEETING

MINUTES OF THE MEETING OF THE LOCAL PROJECT MONITORING COMMITTEE (LPMC) OF LGU-HINUNANGAN, SOUTHERN LEYTE HELD ON JUNE 22, 2026 AT 9:00 AM AT BAC OFFICE, GROUND FLOOR, NEW MUNICIPAL BUILDING, HINUNANGAN, SOUTHERN LEYTE.

ATTENDANCE:

Present

Hon. Rhett T. Binghoy					LPMC Chairman

Hon. Agricola Itom					Member-Punong Barangay

Hon. Jaqueline Y. Balud					Member- Punong Barangay

Hon. Reynaldo R. Alas					Member- Punong Barangay

Victoria Jessica R. Padolina				Member- MLGOO

Felix B. Salinas						Member- CSO Representative

Engr. Armando M. Notarte				Member- Municipal Engineering

Jocelyn D. Reytas					Member- Mun. Budget Officer/

Mun. Accountant - Designate

Engr. Alenita M. Engcoy				MPDC-LPMC Secretary

Cherry P. Frias						MPDC Staff/LPMC Secretariat

Absent

Danilo Aclon						Member-CSO Representative

(Attendance sheet is hereto attached)

==========================================================================================

I – Calendar of Business:

- The meeting started with an opening prayer led by Hon. Jacqueline Y. Balud, Member – Punong Barangay of Tawog

- After the prayer, Hon. Rhett T. Binghoy/LPMC Chairman requested the LPMC Secretary to do the roll call.

- After the roll call, Hon. Rhett T. Binghoy/LPMC Chairman, declared a quorum at exactly 9:45  AM with six (6) members, one (1) MLGOO, one (1) Chairman, LPMC Secretary and one staff of the secretariat of the Local Project Monitoring Committee confirmed present.

- The Chairman asked for a motion to read the previous minutes.

- Hon. Agricola M. Itom– LPMC Member, moved to read the previous minutes and duly seconded by Hon. Jacqueline Y. Balud, LPMC Member.

- Engr. Alenita M. Engcoy, LPMC Secretary read the previous Minutes.

- After the reading of previous minutes, the Chairman asked the Body if there are some corrections/suggestions to the previous minutes.

- Mr. Reynaldo R. Alas requested a correction to the previous minutes of meeting regarding his middle initial.

- He clarified that his correct middle initial is R, not C.

- The secretary acknowledged the correction.

- The Chairman asked the Body if there are other corrections/suggestions to the previous minutes.

- Since there is none, the Chairman asked for a motion for the approval of previous minutes of LPMC Meeting.

- Mr. Reynaldo R. Alas moved for the approval of previous minutes of LPMC meeting which was duly seconded by Hon. Jacqueline Y. Balud, Punong Barangay of Tawog.

- Since there is no objection for the motion, therefore, the minutes of the previous LPMC meeting held on March 25, 2026 was APPROVED.

- The Chairman then requested Engr. Armando M. Notarte to present the status of project implementation for the second quarter calendar year 2025.

- Engr. Armando M. Notarte presented the Project Accomplishment Report as of June 22, 2026.

- Engr. Notarte informed the Body that the presentation was already improved, composed of many columns since it was requested during the previous meeting to have a detailed presentation.

- Engr. Armando M. Notarte then proceeded with the presentation of the project status and accomplishment.

Project Title					Status/% Accomplishment

- Construction of Hinunangan Public Market			95% ongoing with suspension

- MLGOO Victoria Jessica Padolina asked why it is still in 95%.

- Engr. Armando Notarte explained that it is near to be finished and the remaining undone is the logo.

- MLGOO Victoria Jessica Padolina asked if the logo is included in the program of works.

- Engr. Notarte responded yes.

- MLGOO Victoria Jessica Padolina asked why does it is indicated with suspension.

- Engr. Alenita M. Engcoy, LPMC Secretary answered that it can’t be removed since the project has already not on the target date.

- MLGOO Victoria Jessica Padolina asked if the suspension is the justification of being late.

- Engr. Alenita M. Engcoy answered that May 11, 2025 was the target date, therefore ongoing suspension must be indicated from May 12 up to the present.

- Hon. Jacqueline Y. Balud, LPMC Member agreed since the target date of completion of the said project was last year.

- MLGOO Victoria Jessica Padolina asked the reason of the suspension.

- Engr. Notarte responded that it was due to lack of funds and the late approval of the loan.

- Construction of Health Center				98.12% Ongoing with suspension

- Construction of Tourism Service Center			85.00% ongoing with time Extension

- Engr. Notarte informed the Body that the project is already finished.

- Engr. Alenita M. Engcoy, asked why the project’s accomplishment status remained at 85% even though the project had already been completed.

- Engr. Notarte explained that the discrepancy was due to a typographical error.

- He assured that he would instruct his staff to revise the accomplishment status from 85% to 100%

- Concreting of Farm to Market Road				97.69% Ongoing with suspension

- Engr. Notarte explained to the Body that the project is almost finished.

- Upgrading of Farm to Market Road Phase II			94.33% On going with suspension

- Engr. Notarte explained to the Body that the Upgrading of Farm to Market Road Phase II is almost finished with minimal correction.

- He also informed the Body that he will visit the project within this week.

- MLGOO Victoria Jessica Padolina inquired whether the LGU had received additional funding for the SBDP.

- Engr. Notarte responded that the LGU had received additional funding amounting to 2.5 million and 5 million.

- MLGOO Victoria Jessica Padolina further asked how the 5 million allocation would be utilized.

- Engr. Notarte answered it was in Tabjon Calag-itan.

- He explained that the 2.5 Million and 5 million is allocated to its circumferential road.

- MLGOO Victoria Jessica Padolina said that she will visit the project together with the Engineering staff next week.

- She also added that during the site visit, it should be on time, and vehicle must be ready and in good operational condition.

- Engr. Notarte responded that they already have proposed transportation intended only for engineering and they are still waiting to be bid.

- Jocelyn Reytas, Mun. Budget officer answered that based on the new procurement vehicle is not for bid, it should be purchased online.

- Engr. Alenita M. Engcoy responded that they have no authority to purchase.

- MLGOO Victoria Jessica Padolina asked Engr. Armando Notarte if the Engineering has no transportation intended for their office.

- Engr. Notarte responded that they don’t have.

- MLGOO Padolina express the need of the transportation in offices especially those who conduct monitoring like Planning and Engineering Office.

- She also asked if how many drivers the LGU has.

- Ms. Jocelyn D. Reytas responded that the LGU has a sufficient number of drivers. However, there are currently no plantilla items specifically designated for drivers. She added that the Sangguniang Bayan has already approved the creation of plantilla positions intended for drivers.

- Engr. Notarte proceeded with his presentation.

- Concreting of Calayugan Barangay Road			100% Completed

- Concreting of Canipaan Barangay Road			100% Completed

- Concreting of Talisay Barangay Road			100% Completed

- Concreting of Matin-ao Barangay Road			100% Completed

- MLGOO Victoria Padolina asked about the exact location of the Road Concreting in Talisay.

- Engr. Notarte responded that the project is located near the residence of MLGOO Victoria Jessica Padolina.

- Ms. Padolina informed Engr. Notarte that the said project has already developed cracks.

- She requested that project quality be strictly prioritized to avoid public perception that no proper monitoring is being conducted.

- Concreting of Sto. Niño I Barangay Road			81.28% Ongoing

- Purchase and Installation of Solar Lights 			100% Completed

Poblacion to Das-ay Bridge

- Rehab./Improvement of Hinunangan Passenger Terminal	70% Ongoing

- Purchase and Installation of Solar Lights 			100% Completed

Poblacion to Bangcas A

- Concreting of Bangcas A Barangay Road			100% Completed

- Concreting of Salog Barangay Road				100% Completed

- Construction of Sto. Niño II FMR				40% Ongoing

- Rehab./Improvement of Sto. Niño II Masaymon –		35% Ongoing

Calinao FMR

- Concreting of Bugho Barangay Road			30% Ongoing

- Construction of Labrador Day Care Center			25% Ongoing

- Construction of Two (2) Storey Multipurpose Building	20% Ongoing

At Barangay Badiangon

- Concreting of Palongpong Barangay Road			40% Ongoing

- Victoria Jessica Padolina asked about the exact location of the installed solar street lights in Barangay Nava.

- She clarified if the solar lights are installed within the barangay proper or along the access road leading to the barangay.

- Ms. Rona Odilao, staff of engineering answered that the solar lights are installed at the barangay proper, near at the barangay hall.

- Victoria Jessica Padolina asked about the total number of solar lights were being installed.

- Ms. Rona Odilao responded that ten (10) solar lights were being installed.

- Victoria Jessica Padolina asked when the solar lights were installed.

- She added that she was at Barangay Nava last May and observed that no solar lights had been installed at that time.

- Engr. Notarte responded that the solar lights were installed in June.

- Concreting of San Pablo Island Barangay Road		40% Ongoing

- Concreting of San Pedro Island Barangay Road		Not Yet Started

- Concreting of Manalog Barangay Road			Not Yet Started

- Rehab./Improvement of Old Municipal Building		Not Yet Started

- Engr. Notarte informed the Body that the Rehab./Improvement of Old Municipal Building has not yet started due to the pending acquisition of a mandatory demolition permit.

- Ms. Victoria Jessica Padolina agreed that the Engineering Office should not commence any work without first securing a demolition permit.

- She also asked whether the Old Municipal Building is classified as a historical site, noting that if it is, a demolition permit may no longer be required.

- Engr. Notarte stated that he would coordinate with and submit a request to the Commission on Audit (COA) regarding the matter.

- Ms. Victoria Jessica Padolina suggested convening a meeting with the Tourism Council first to determine the status of the building before elevating the matter to COA.

- Engr. Alenita M. Engcoy responded that COA could not determine or record the building's status because it was constructed in 1845.

- Ms. Victoria Jessica Padolina stated that, under the Local Government Code, the municipality is required to submit an annual inventory of its properties.

- Consequently, it was agreed that, in the absence of such an inventory, a meeting with the Tourism Council would be convened to discuss the possibility of passing a resolution authorizing the demolition of the building.

- Hon. Jacqueline Y. Balud, LPMC Member, stated that the building is already structurally deteriorated and has narrow staircases.

- Engr. Notarte responded that their office has already prepared action plans for both options, whether the building will demolished or restored.

- Victoria Jessica Padolina stated that keeping the building in its current state is not an option.

- She added that the structure is too cramped, emphasizing that it must be expanded and improved to meet engineering standards.

- Engr. Engcoy responded that the structure of the building cannot be altered.

- Engr. Notarte also added that the design of the building is coordinated with the tourism office.

- Victoria Jessica Padolina stated that the engineering must follow the building standards.

- She also stated that based on DPWH guidelines and the National Building Code, all structures must comply with established engineering safety standards.

- Hon. Agricola Itom, LPMC Member responded that the building has already survived several earthquakes without collapsing.

- Victoria Jessica Padolina also responded that the structural strength is not the problem.

- She added that the entrance and stairs are too narrow to pass engineering standards.

- Hon Rhett T. Binghoy, LPMC Chairman, asked if the SLP Building near the Old Municipal Building will be removed.

- Victoria Jessica Padolina responded that if the SLP have building permit, no need to remove them, but if they have none, the structure must be demolished.

- Victoria Jessica Padolina, clarified with Engr. Notarte if the budget allocated for the Rehab./Improvement of the Old Municipal Building was only Two Million Pesos (Php 2,000,000.00)

- Engr. Notarte responded that the allocated amount is Two Million Pesos (₱2,000,000.00) and that it is intended for Phase I of the project.

- Engr. Alenita M. Engcoy, also responded that the allocated amount would only cover the initial demolition and stripping works.

- Hon. Rhett T. Binghoy asked if wood would still be used for the project since the original floor of the building is wood.

- Engr. Notarte responded thst wooden components would be utilized, provided that the project’s scope is limited to pure restoration and historic preservation.

- Engr. Notarte proceeded with his presentation.

- Construction of  Concrete Drainage Canal with Cover		Not Yet Started

At Barangay Poblacion

- Victoria Jessica Padolina, asked if the Construction of Concrete Drainage Canal with Cover at Barangay Poblacion is the specific project that the residents complain about.

- The Body responded yes.

- Concreting of Salvacion Barangay Road				Not Yet Started

- Rehab./ Improvement of Municipal Children’s			Not Yet Started

Playground

- Victoria Jessica Padolina asked about the completion date of the projects.

- Engr. Notarte responded that the completion date is in August.

- Construction of Two (2) Storey Multipurpose Building		Not Yet Started

At Barangay Tawog

- Victoria Jessica Padolina, asked if that was the only project for the last quarter.

- Engr. Engcoy responded yes.

- She also explained that they are only reporting the status of the current projects.

- Engr. Notarte proceeded on presenting the pictures during the site inspection.

- After the presentation of the Photos during site inspection, Hon. Rhett T. Binghoy presented the Department of Public Works and Highways (DPWH) Projects Fiscal Year 2026.

- Construction of Multipurpose Building Barangay			100% Completed

Labrador, Hinunangan, Southern Leyte

- Construction (Completion) of Multipurpose Building		100% Completed

Barangay Poblacion, Hinunangan, Southern Leyte

- Hon. Rhett T. Binghoy, asked about the exact location of the project within Barangay Labrador.

- Victoria Jessica Padolina suggested that it would be beneficial to include project coordinates in the reports to easily verify the exact location of the projects.

- Engr. Alenita M. Engcoy, LPMC Secretary, agree to the suggestion that utilizing coordinates would facilitate the efficient tracking and location projects.

- Construction of 1 Storey 2 Classroom School				100% Completed

Building Catublian, Hinunangan, Southern Leyte

- Hon. Reynaldo R. Alas, LPMC Member and Punong Barangay of Catublian, reported that there are minor works that need to finish.

- Construction (Completion) of Multi-Purpose Building		86.34%

Barangay Canipaan, Hinunangan, Southern Leyte

- Construction of Multi-Purpose Building Barangay			93.94%

Calayugan, Hinunangan, Southern Leyte

- Construction of Barangay Nueva Esperanza Road, 			85.17%

Hinunangan, Southern Leyte

- Construction of Sto. Niño 1 – Salvacion (Sitio Dagmol)		67.76%

Road

- Construction of 1 Unit – Storey – 2 Classroom School			100%

Building in Canipaan National High School

- Construction of 1 Unit-Storey- 2 Classroom School			100%

Building in Otama Elementary School

- Concreting of Sitio Dagmol, Brgy. Salvacion FMR			100%

- Construction of 1 Unit-Storey-3 Classroom School			100%

Building Sto. Niño II National High School

- Hon. Rhett T. Binghoy, LPMC Chairman, consulted the body of what actions to be taken.

- Victoria Jessica Padolina suggested to visit each projects.

- The Body agreed to the suggestion.

148. Engr. Alenita M. Engcoy, LPMC Secretary, then suggested that the Local Government Unit (LGU) tap with the national agencies for technical assistance in monitoring local projects.

149. Victoria Jessica Padolina clarified that national agencies might not readily accommodate this request, emphasizing that the primary mandate for local project monitoring rests solely with the LPMC.

150. Mr. Felix Salinas, LPMC Member and CSO Representative, recommended agricultural or farm-related infrastructure projects in the committee’s monitoring scope.

151. Hon. Rhett T. Bighoy, LPMC Chairman stated that agricultural projects fall under the jurisdiction of the National Irrigation Administration (NIA)

152. Victoria Jessica Padolina responded that agricultural projects could still be integrated into the LPMC’s tracking list, given their direct implementation at the barangay level.

153. Engr. Armando Notarte, proceeded on the Orientation on Basic Engineering Terms Vital to Contract Implementation.

154. He explained that the said orientation will serve as a foundational guide to help the Local Project Monitoring Committee (LPMC) effectively monitor government infrastructure projects.

155. He also explained to the Body that the committee’s primary mandate is to observe, verify documents, and report on project quality, budgets and timeline.

156. He added that members are not expected to perform actual engineering designs.

157. He also explained in detail critical contractual documents and administrative process that members must track, including the Program of Works (POW), Bill of Quantities, Notice to Proceed, Change Orders, and Time Extensions.

158. After the presentation, Hon. Rhett T. Binghoy, asked the MLGOO, Victoria Jessica Padolina, if it is possible to avail gasoline allowance for the Monitoring Committee.

159. Victoria Jessica Padolina explained that fuel allowance had been granted during tenure in the municipality of Silago.

160. She added that the LGU is currently budgeting for FY 2027, the committee could formally propose budget allocation of LPMC.

161. Hon. Agricola Itom asked if the requested fuel allowance could be charged to Bids and Award Committee (BAC) funds.

162. Hon. Binghoy responded that such arrangements are not permissible.

163. Victoria Jessica Padolina explained that a fuel allowance for monitoring committee is not mandatory and should be based on the availability of funds of the LGU.

164. The Chairman asked if there is any other concern to be taken up.

165. Since there is none, Hon. Agricola Itom, LPMC Member moved to adjourn the meeting and duly seconded by august Body.

- The meeting was adjourned at exactly 11:46 pm.

===========================================================================

Certified Correct:

ENGR. ALENITA M. ENGCOY

MPDC/Secretary

Approved:

HON. RHETT T. BINGHOY

LPMC Chairman