Republic of the Philippines

Province of  Southern Leyte

Municipality of Silago

PROJECT MONITORING  COMMITTEE (PMC)

MINUTES OF THE MEETING OF THE PROJECT MONITORING COMMITEE) OF THE MUNICIPALITY OF SILAGO, SOUTHERN LEYTE HELD ON march 19, 2026 at 11: 00 AM, AT VIAJEROS HOTEL AND RESTO.

PRESENT:

HON. ROLANDO  P. PAMUGAS            PMC MEMBER/ PUNONG BRGY. MERCEDES

ENGR. EUTIQUIO R. BELOY                   PMC SECRETARIAT / MPDC

MR. DANILO P. TAGGET                         PMC  MEMBER/CSO

HON.  DANNY RAMA                               PMC MEMBER / PUNONG BRGY, TUBOD

MR.  DENNIS C. PADOLINA                   PMC VICE-CHAIRPERSON

MRS. MARILYN DALUMPINES                PMC /CSO

ENGR. BERNIE DEMIAO                           ENGR. 1

ARCHITECT  CHARITY MATE                 MUN. PLANNING 1

ENGR. RUBY G. ANSALE                            ASSISTANT ENGR.

ABSENT ;

HON. ROGELIO C. ALIPIO                        PMC CHAIRPERSON

MRS.MARILYN DALUMPINES                CSO/PMC MEMBER

PRESENTATION OF AGENDA	:PMC Chairman

- Joint site inspection on various implemented infrastructure projects.

- Presentations on the findings, comments and recommendations project.

CALL TO ORDER

After the actual joint inspection, The meeting of PMC  was called to order by the   Presiding Officer  MLGOO DENNIS C. PADOLINA   at 11:00 o clock in the morning.

BUSINESS OF THE DAY

- Projects  Inspection

- COMPLETION  OF THE REMAINING OF SILAGO YOLANDA PERMANENT HOUSING PROJECT.

- TUNNEL VENT POULTRY (BUILDING 2)

- CONSTRUCTION OF WHALE BONE MUSEUM

- CONSTRUCTION OF MULTI-PURPOSE SITIO LO-OK, MERCEDES

- CONSTRUCTION OF  NATIONAL DEVELOPMENT CHILD CENTER (NCDC)

- CONSTRUCTION OF NEW  MUNICIPAL BUILDING

- CONSTRUCTION OF TUNNEL VENT POULTRY ( BUILDING 2) This project is 60% accomplished and is currently ongoing. The roofing of the building is not fully completed and the flooring  40% of whole area is not yet finished .

MLGOO Denis Padolina noticed that some of the workers were not doing any work.

CSO/PMC Member Danilo Tagget answered that it might snacks time because he saw

somebody eating snacks that is why they are  not doing any work.

- COMPLETION  OF THE REMAINING OF SILAGO YOLANDA PERMANENT HOUSING PROJECT. The project is about 60% accomplished, and work is still on-going. Some of the units are close to completion — the toilet bowls have already been installed, and the walls are  already painted.

- CONSTRUCTION OF WHALE BONE MUSEUM. The project is about 30% accomplished  and still on-going construction .

The PMC Member declared that the project has no issues.

- CONSTRUCTION OF MULTI-PURPOSE SITIO LO-OK, MERCEDES. The project is  65% accomplished and still on-going project.

It was observed by a PMC members that the welder was not wearing safety gear

while welding on top of the post.

Hon. Rolando Pamugas responded that he keeps reminding the worker to wear safety gear,

but the worker refuses, saying the gear is too heavy and makes it uncomfortable to work.

- CONSTRUCTION OF  NATIONAL DEVELOPMENT CHILD CENTER (NCDC).The project is 5% accomplished and on-going project .

PMC Members suggested that the project billboard should be post in the site and also the

Members suggested to construct an stockroom for  construction materials.

- CONSTRUCTION OF NEW MUNICIPAL BUILDING.The project is no on-going development /no activity .

MLGOO Dennis C. Padolina suggested to make a resolution address to the implementing agency  ,inquiring on when the exact date the project started .

PMC Members aggreed the suggestion of MLGOO Dennis C. Padolina.

Since the there is no other recommendation of all the  implemented projects .It was then

moved  ‘by PMC Member Hon. Dewah A. Potol  and seconded by  Hon. Santos Labrador.

- ADJOURNMENT

There is no further business , the meeting was adjourned   at 12;30 o clock at noon  through

the motion of PMC Member Hon. Danny Rama and duly seconded Masse

ENGR. EUTIQUIO R. BELOY  JR.

MPDO/PMC Secretariat

Attested ;HON. ROGELIO  C. ALIPIO

PMC CHAIRPERSON

LNB PRES/PUNONG BRY. SUDMON